## Sheet1
RICH1 HPD Plan 11-01-07
Item | Sub Group | From | To
Ladder Mechanics
U channels - manufacture | all | complete
U channels - annodising | 28 | complete
| 4 | 2007-02-19 | 2007-02-23
Rungs - manufacture |  | complete
Rungs - Annodising |  | complete
Rungs -alterations |  | complete
End Pieces - Manufacture | initial 10 | complete
| remaining 22 | 2007-01-15 | 2007-02-01
End Pieces - Annodising | initial 10 | 2007-02-19 | 2007-02-23
| remaining 22 | 2007-02-05 | 2007-02-09
| swap at CERN | 2007-02-12 | 2007-02-16
Adapter Plates - manufacture | initial 2 | completed
| remaining 12 | 2007-01-12 | 01/02/07?
Cable Guides |  | 2007-01-22 | 2007-03-10
Data Patch Panels | cut plastic | ? | 2007-03-10
| Data bulkheads | complete
| TTC bulkheads | complete
| RJ45 bulkheads | complete
| 37pin Sub D | complete
Voltage Patch Panel
High Voltage Patch Panel
Ladder Assembly @ CERN | 2 prototypes | complete
| 5 to complete half | 2007-01-16 | 2007-01-18
| 9 to finish ladders | 2007-02-26 | 2007-02-27
Electronics
HV boards Deliverd to CERN
LV Boards Deliverd to CERN
L0 boards
HPDs
Data fibres Deliverd to CERN |  | complete
TTC fibres Deliverd to CERN |  | complete
Top HPD Frame
Design |  |  | 2007-01-19
Ordering/Delivering Materials |  | 2007-01-22 | 2007-02-02
Construction |  | 2007-02-05 | 2007-03-09
Preliminary aspirations depending on HV delivery etc
Ladder Dressing |  |  |  | Testing assumes 2.5 days to bring up HV and perform tests
|  | this from 1.5 cols a week |  | this from 2 cols a week
Top Crate 7 |  | 2007-02-01 | 2007-03-10 | 2007-02-01 | 2007-02-28
Bottom Crate 7 |  | 2007-03-12 | 2007-04-13 | 2007-02-28 | 2007-03-23
Spare 2 |  | 2007-04-16 | 2006-04-21 | 2007-03-26 | 2007-03-30
Ladder 1 | HV chain | complete
| LV boards | complete
| L0 boards | complete
| Cabeling | 2007-01-18 | 2007-01-18
| HPDs | 2007-02-01 | 2007-02-01
| Testing | 2007-02-05 | 2007-02-07
Ladder 2 | HV chain | 2007-01-22 | 2007-01-24
| LV boards | 2007-02-05 | 2007-02-06 | LV mounting Starts
| L0 boards | 2007-02-01 | 2007-02-01
| Cabeling | 2007-02-02 | 2007-02-02
| HPDs | 2007-02-06 | 2007-06-07
| Testing |  |  | 2007-02-07 | 2007-02-09
Ladder 3 | HV chain |  |  | 2007-01-24 | 2007-01-26
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-02-12 | 2007-02-14
Ladder 4 | HV chain |  |  | 2007-01-29 | 2007-01-31
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-02-14 | 2007-02-16
Ladder 5 | HV chain |  |  | 2007-01-31 | 2007-02-02
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-02-19 | 2007-02-21
Ladder 6 | HV chain |  |  | 2007-02-05 | 2007-02-07
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-02-21 | 2007-02-23
Ladder 7 | HV chain |  |  | 2007-02-07 | 2007-02-09
LV boards
L0 boards
Cabeling
HPDs
| Testing |  | 2007-03-10 | 2007-02-26 | 2007-02-28
Ladder 8 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing | 2007-03-12 |  | 2007-02-28 | 2007-03-02
Ladder 9 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-03-05 | 2007-03-07
Ladder 10 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-03-07 | 2007-03-09
Ladder 11 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-03-12 | 2007-03-14
Ladder 12 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-03-14 | 2007-03-16
Ladder 13 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  |  | 2007-03-19 | 2007-03-21
Ladder 14 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  | 2007-04-13 | 2007-03-21 | 2007-03-23
Ladder 15 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing | 2007-04-16 |  | 2007-03-26 | 2007-03-28
Ladder 16 | HV chain
LV boards
L0 boards
Cabeling
HPDs
| Testing |  | 2007-04-21 | 2007-03-28 | 2007-03-30
Cooling Plate Assembly | All | 2007-01-15
Collumns mounted in top crate | 2007-03-12 | 2007-03-16
Top crate mounted in RICH1