## Sheet1
QNS
| Resources |  | Are Scott, Dan, Phil, John Back, Mike Perkins available?
| Tasks | Who? | Comment
1 | General
1.01 | MEBT optics design | Morteza | Morteza to take over from Chip. Need optics simulation using simulated RFQ beam.
1.02 | MEBT beam dynamics | Morteza | Macthing beam from RFQ to MEBT. Rotation of chopping plane.
1.03 | Support structures | Pete, Alberto
1.04 | Component datums | Dave Wilsher | Consult with at design stage
1.05 | Component alignment | Jim Loughrey, Adrian Hooper | Consult with at design stage - Adrian to revisit FETS datums prior to RFQ instasllation
1.06 | Cooling | Duncan Couchman | Design of RFQ cooling underway
1.07 | Power | Mike Perkins? | Need electrical services contact
1.08 | Link to OM | Alberto | Peter Clarke, Richard Day etc.
1.09 | MEBT beam pipe |  | Designed around KF40
1.1 | MEBT beam scrapers |  | Protect chopper plates by scraping off beam halo using water cooled scrapers.
1.11 | Overview CAD model | Pete, Alberto | One model, probably held by Pete
1.12 | LEBT spectrometer | Juergen, Pete, Saad | Initial test look positive
2 | Project Engineering
2.01 | Function | N/A | To get the MEBT built on time and to within budget
2.02 | Description | N/A | Assigining tasks to the right people and checking on progress.
2.03 | Time | Pete, Alberto
2.04 | Budget | Alan, Juergen, Pete
3 | Shielding
3.01 | Function |  | To protect us from radiation
3.02 | Description |  | Large concrete blocks arranged to enclose RFQ and MEBT
3.03 | Calculations | Alan, Juergen
3.04 | Risk assessment | Alan, Dan, Juergen | Dan is radiation safety officer for R8
3.05 | Interlocks | Alan, Mike Perkins
3.06 | Purchasing | Alan
3.07 | Installation | John Govans | Take advice from installers
RF System
| Function | N/A | To transport RF power from the Klystron to the RFQ and MEBT
| Description | N/A | Waveguide (Mega Industries W2300) followed by coaxial cable
| Purchasing | Saad, Alan
| Design | Saad, Pete
| Waveguide installation | John Govans | Circulator arrived, waveguide on the way.
| Waveguide testing | Saad
| Coax specification | Saad
| Coax installation | John Govans
| Commissioning | Saad
| RF Couplers | ESSB | Six (2 RFQ + 4 MEBT) + 2 etxra for RFQ if power density is too high
| Function | N/A | To introduce RF power into accelerating structures
| Description | N/A | Tapered coax line terminating in water cooled loop
| RF / EM Simulations | Juanlu
| Engineering design | ESSB, Alberto
| Prototype manufacture | ESSB
| Testing |  | Someone with a Klystron!
| Manufacture | ESSB
Power requirements
| Cooling | Duncan Couchman
Chopper
| Function |  | To create precise gaps in the beam
| Description |  | Series of electrodes within vacuum vessel
| Length |  | ~450mm
| EM design | Mike Clarke-Gayther
| Optics design | Mike Clarke-Gayther
| Electrode design | Mike Clarke-Gayther | Helical prototype, planar prototype
| Engineering design | RAL Engineer
| Manufacturing | External co. | Mike to advise.
Testing
Commissioning
| Electrical requirements |  | Pulse generators, low level controls, cabling
| Vacuum |  | Mount for vacuum pump
Support structure
| Alignment tolerances |  | Mike to advise.
| Chopper beam dumps |  | 2 required - see CERN and SNS designs
| Function |  | Place where chopped beam is dumped into.
| Description |  | Vacuum vessel with moveable water cooled target and mount for vacuum pump.
| Length |  | ~ 450mm
| How many bunches? |  | Fast chopper removes two sets of three adjacent bunches. Slow chopper removes central set.
| Chopping orientation |  | Vertical - unidirectional for both choppers?
| Material |  | Target = good thermal conduction + low radiation = aluminium. May require coating to prevent sputtering.
| Specification | Mike Clarke-Gayther | Lengths, angles from chopper
| Thermal simulation | Scott, Dan
| Engineering design | Alberto
| Manufacture | RAL, HEP workshop
Support structure design
| Support structure manufacture | External co.
| Cooling |  | Not much required.
| Vacuum |  | Pump at this higher pressure location.
| Rebuncher Cavities |  | 4 required, designed and built in partnership with whom?
| Function |  | To bunch the beam (by slowing particles at the head of the bunch and speeding up particles at the back of the bunch).
| Description |  | Water cooled copper cylinders with re-entrant noses.
| Length |  | ~200mm
| EM design | Was Chip | Need to know who are our partners ASAP - ESSL? ESSB?
| Frequency / tolerance studies | Saad
| Thermal simulations | WHO?
| Tuning system design | Saad
| Cold model design |  | Do we want one?
| Cold model testing |  | LLRF? Bead pull?
Engineering design
Support structure design
| Support structure manufacture | External co.
Manufacture
Testing / commissioning
| Quadrupoles |  | Eleven required, common design, let's get one made and test it ASAP
| Function |  | To focus or de-focus beam (and steer?)
| Description |  | Water cooled (possibly) quadrupole
| Length |  | ~70mm
| EM design | John Back
| Novel or standard design? |  | Need approach manufacturers ASAP
| Specification |  | Magnetic field strength, bore, Z length
Power
| Cooling | Duncan Couchman | If standard design is chosen
| Magnetic field map check | Daresbury, Imperial | Imperial may have system in place by then.
| Manufacture | External co.
Beam Position Monitors
| Function |  | There's a clue in the name.
| Description |  | Short flanged vacuum tube
| Design | Simon, UCL
| Readout | Simon, UCL
| Manufacture | Simon, UCL
Fixed diagnostics
| Function |  | To inspect beam at the end of the MEBT.
| Description |  | Vacuum vessel with laser system inbetween large dipole (to deflect beam).
| 2D vessel design | Christoph
| 3D vessel design | RAL Engineer
| Magnet design | External co, John Back | Approach companies this summer.
| Magnet manufacture | External co.
| Magnet field map check | Daresbury, Imperial | Imperial may have system in place by then.
Magnet support design
Magnet support manufacture
| Vessel manufacture | External co.
| Vessel internals specification | Christoph | Heason stages, optics mounts, beam dumps
| Vessel internals purchasing | Christoph
| Laser specification | Christoph
| Laser purchasing | Christoph
| Laser safety | Christoph
| Shielding and interlocks | WHO?
Cooling for bending magnet
Detector / readout
Power
| Moving diagnostics |  | Beam is ~25mm diameter in MEBT versus ~ 80mmdiameter in LEBT.
| Function |  | To inspect the beam at different places along beam line
| Description |  | Existing diagnostics with modifications to suit MEBT.
| Adapt existing |  | Insufficient funding or staff for new diagnostics
| Existing slit slit scanners |  | Should work fine - resolution 0.1mm?
| Pepperpot |  | Too large for MEBT beam. Consider new build.
| Profile |  | Useful to have. Quartz may take higher power density.
| Camera position |  | Needs to be moved closer to head due to smaller beam. Investigate.
| Beam dumps |  | One completed by TEKNIKER - in transit
| Function |  | To stop / absorb beam
| Description |  | Water cooled aluminium cone.
| Cooling | Duncan Couchman
| Support structure | Pete, Alberto