## Project Monitor Form

| Project: Calice | PMF number: 0021 |  |  |
| --- | --- | --- | --- |
| Date: 12-December-2003 | Sheet: 1 | of | 3 |
| # News and comment |  |  |  |
| Dates; The minutes and presentations of the Calice Electronics Meeting held on Tuesday 9th December at RAL are now available on the Calice UK Web site at http://www.hep.ph.ic.ac.uk/calice/elecMeetings/meetings.html - the next meeting is on Monday 12th January at 1pm at RAL. Procurement status; The QDR memories are due to arrive at the end of December – this is not on the critical path as we can work around the problem. No new info on this date as yet. We need to check the delivery date for the parallel jumpers. We will procure production quantities of the SCSI connectors for the VFE. Test & Firmware status; Work has continued on three fronts - Software development with the CMS Tracker FED using the existing FED firmware, RS232 readout on the CERC and chipscope/VIO development with the FE FPGA firmware on the CERC looking at the ADC & DAC. Additionally work is ongoing on the VME-BE-FE Firmware integration – the work is not on the critical path at present. The use of chipscope/vio with the FE FPGA firmware has been successfully established. The integration of the RS232 readout with the FE FPGA design has been started but not completed. This work will not fully resume until the first week of January due to annual leave. The expected date for VFE tests is now the week starting 19th January QA documentation status; Distribution of version 0.2. Project Spec is still outstanding. |  |  |  |

| # Actions from the previous PMF |  |  |  |
| --- | --- | --- | --- |
| Action | Status | Who | Target date |
| Check on web location of CMS VME documentation | Not available yet | RH | 19-12-2003 |
| Work on Integration of Chipscope & VIO cores with FE FPGA code | ### Done | EF | 5-12-2003 |
| Provide support & consultancy for testing as required | Ongoing | IC/SAB | 19-12-2003 |
| Provide consultancy for BE/VME FPGA | Ongoing | ST/EF | 19-12-2003 |
| Investigate VFE availability & Test Plans | Done | SAB/PD | 12-12-2003 |
| Confirm QDR Delivery | Ongoing | SAB | 12-12-2003 |
| Make sure Route Cards & Problem Reports up to date | Ongoing | SAB | 12-12-2003 |
| Order 128MB Compact Flash cards, 11 Off | Ongoing | RH | 12-12-2003 |
| Update Project Spec and sign off | Ongoing | RH | 19-12-2003 |

| # Actions outstanding and new actions |  |  |
| --- | --- | --- |
| Action | Who | Target Date |
| E-mail web location of CMS VME documentation to Paul Dauncey | RH | 19-12-2003 |
| Arrange a meeting with Dave Mercer to discuss Final Firmware development | RH | 19-12-2003 |
| Provide support & consultancy for testing as required | IC/SAB | 19-12-2003 |
| Investigate & provide support for power sequencing issues | JS | 19-12-2003 |
| Provide consultancy for BE/VME FPGA | ST/EF | 19-12-2003 |
| Confirm QDR Delivery | SAB | 19-12-2003 |
| Make sure Route Cards & Problem Reports up to date | SAB | 19-12-2003 |
| Order 128MB Compact Flash cards, 11 Off | RH | 19-12-2003 |
| Investigate VFE availability & Test Plans | SAB/PD | 19-12-2003 |
| Update Project Spec and sign off | RH/PD | 15-12-2003 |

Project Monitor Form- milestones

| Project: Calice |  | PMF number: 21 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager: Rob Halsall |  |  |  |  |  |  |
| Date: 12-December-2003 |  | Sheet: 3 |  | of | 3 |  |
|  | Milestones from Project Management Plan Version: | date due in PMP | predicted date |  |  | date done |
| 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 | Project Spec Sign Off Prototype Design Complete Prototype Fabrication Complete Prototype Testing Complete Design Iteration Complete Production Board Fabrication Complete Production Board Testing Complete PCB tape out Assembled PCB at RAL Module ready for FPGA development (earliest) Basic ADC performance tests firmware ready Basic ADC performance tests complete Ready for VFE tests VFE Test complete Final firmware development start FE-BE FPGA Integration Complete | ------------- | 7-11-2003 24-10-2003 17-11-2003 31-03-2004 31-04-2004 31-05-2004 30-07-2004 24/10/03 14/11/03 18/11/03 18/11/03 12/12/03 05/12/03 12/12/03 06/11/03 03/12/03 |  |  | 23-10-2003 21-11-2003 27-11-2003 |