## Project Monitor Form

| Project: Calice | PMF number: 0022 |  |  |
| --- | --- | --- | --- |
| Date: 19-December-2003 | Sheet: 1 | of | 3 |
| News and comment |
| Dates; RAL will be shutdown from the 25th December. First day back will be Monday the 5th January 2004. The next meeting is on Monday 12th January at 1pm at RAL. The next PMF will be on the 9th of January 2004. Procurement status; The QDR memories are due to arrive at the end of December. The Parallel jumpers have arrived. The procurement of SCSI connectors for the VFE needs to be actioned. Test & Firmware status; At RAL using the Chipscope, VIO and front end firmware a problem with the DAC to DIFF OP-AMP to ADC differential matching has been discovered. This limits the range through which the DAC can be tracked. There is at least one likely fix for this problem that if confirmed would not be too difficult to implement. Work has continued at RAL, UCL & IC with the RS232 daq but has not got as far as being able to control readout the ADC/DACs. Work has continued with the VME-BE-FE firmware integration at UCL & Manchester but CAE tool problems have been encountered preventing proper compilation of the design. The expected date for VFE tests is now the week starting 19th January QA documentation status; Distribution of version 0.2. Project Spec is still outstanding. |

| Actions from the previous PMF |
| --- |
| Action | Status | Who | Target date |
| Check on web location of CMS VME documentation | Not available yet | RH | 19-12-2003 |
| Provide support & consultancy for testing as required | Ongoing | IC/SAB | 19-12-2003 |
| Provide consultancy for BE/VME FPGA | Ongoing | ST/EF | 19-12-2003 |
| Confirm QDR Delivery | Ongoing | SAB | 12-12-2003 |
| Make sure Route Cards & Problem Reports up to date | Ongoing | SAB | 12-12-2003 |
| Order 128MB Compact Flash cards, 11 Off | Ongoing | RH | 12-12-2003 |
| Update Project Spec and sign off | Ongoing | RH | 19-12-2003 |

| Actions outstanding and new actions |
| --- |
| Action | Who | Target Date |
| E-mail web location of CMS VME documentation to Paul Dauncey | RH | 19-12-2003 |
| Arrange a meeting with Dave Mercer to discuss Final Firmware development | RH | 19-12-2003 |
| Provide support & consultancy for testing as required | IC/SAB | 19-12-2003 |
| Investigate & provide support for power sequencing issues | JS | 19-12-2003 |
| Provide consultancy for BE/VME FPGA | ST/EF | 19-12-2003 |
| Confirm QDR Delivery | SAB | 19-12-2003 |
| Make sure Route Cards & Problem Reports up to date | SAB | 19-12-2003 |
| Order 128MB Compact Flash cards, 11 Off | RH | 19-12-2003 |
| Investigate VFE availability & Test Plans | SAB/PD | 19-12-2003 |
| Update Project Spec and sign off | RH/PD | 15-12-2003 |

Project Monitor Form- milestones

| Project: Calice | PMF number: 22 |  |  |
| --- | --- | --- | --- |
| Project Manager: Rob Halsall |  |  |  |
| Date: 19-December-2003 | Sheet: 3 | of | 3 |
|  | Milestones from Project Management Plan Version: | date due in PMP | predicted date | date done |
| 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 | Project Spec Sign Off Prototype Design Complete Prototype Fabrication Complete Prototype Testing Complete Design Iteration Complete Production Board Fabrication Complete Production Board Testing Complete PCB tape out Assembled PCB at RAL Module ready for FPGA development (earliest) Basic ADC performance tests firmware ready Basic ADC performance tests complete Ready for VFE tests VFE Test complete Final firmware development start FE-BE FPGA Integration Complete | ------------- | 7-11-2003 24-10-2003 17-11-2003 31-03-2004 31-04-2004 31-05-2004 30-07-2004 24/10/03 14/11/03 18/11/03 18/11/03 12/12/03 05/12/03 12/12/03 06/11/03 03/12/03 | 23-10-2003 21-11-2003 27-11-2003 |