Project Specification

Project Name: Tera-Pixel APS for CALICE

### Scope: WP-3

Version:  1.0

APPROVAL

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager | Jamie Crooks |  |  |
| Customer/Sponsor | Paul Dauncey |  |  |

DISTRIBUTION:

| Project Manager: | Jamie Crooks |
| --- | --- |
| Customer/Sponsor: | Paul Dauncey |
| Group Leader responsible for the project: | Renato Turchetta |
| Division Head responsible for the project: | Marcus French |
| Project Managers of related projects: |  |
| Programme Manager: |  |
| Quality Manager: | Steve Quinton |

1	DESCRIPTION

This document defines the full extent of effort for the WP3 MAPS for CALICE project, covering RAL Technology, RAL PPD, Imperial College London and University of Birmingham. For the purpose of this document, Imperial and Birmingham appear as subcontractors. Indication of assignment of responsibilities is included where relevant.

The WP3 project aims to establish the feasibility of MAPS as a basis for an electromagnetic calorimeter. This is being done within the context of International Linear Collider (ILC) detector developments and in particular within the CALICE collaboration. The project was funded for the period up to the end of FY08/09 with a total budget of £1034k.The full text of the CALICE proposal and WP3 description can be found at http://www.hep.ph.ic.ac.uk/calice/

  - Related Documents

- Project Management Plan: Written specifically to cover the ASIC design work only, which will be undertaken and managed within the EID QA system.

- ASIC1 Technical Specification: Approval as for Project Specification document

- ASIC2 Technical Specification: To be written & approved July 2007 (see Gantt chart)

- ASIC1 Testing Specification

- Risk Management Plan

- Stakeholder Plan

2	SCOPE

  - Includes

| Item | Responsibility |
| --- | --- |
| Feasibility study & report | RAL Technology |
| Specification of ASIC1 | RAL Technology |
| Specification approval | Customer |
| Design work (ASIC1) | RAL Technology |
| Interim & final pixel/die NWELL profiles for physics simulations | RAL Technology |
| Device simulations to support design choices during design | RAL PPD |
| Physics simulations to support design choices during design | Birmingham, Imperial |
| Selection of PCB/assembly house & agreement of bond pad specifications | Imperial, RAL Technology |
| Non-wirebonding feasibility/technique search | RAL Technology |
| Peripheral/example PCB circuit schematics | Imperial, RAL Technology |
| DAQ test system for ASIC1 | Imperial, RAL Technology |
| PCB assembly for ASIC1 | Birmingham, Imperial |
| Non-wirebonding tests (see Testing Specification document) | RAL Technology |
| Basic tests ASIC1 (see Testing Specification document) | RAL Technology |
| Detailed tests: ASIC1 (see Testing Specification document) | Birmingham, Imperial, RAL PPD |
| Specification of ASIC2 | RAL Technology |
| Specification approval | Customer |
| Design work (ASIC2) | RAL Technology |
| DAQ test system for ASIC2 | Imperial, RAL Technology |
| PCB assembly for ASIC2 | Birmingham, Imperial |
| Basic tests ASIC2 (see Testing Specification document) | RAL Technology |
| Detailed tests: ASIC2 (see Testing Specification document) | Birmingham, Imperial, RAL PPD |
| Design of beam test PCB | Birmingham |
| Beam test PCB FPGA design | Birmingham, RAL PPD |
| Beam test PCB assembly | Birmingham |
| Beam test DAQ system firmware | Imperial |
| Beam test operations and data analysis | Birmingham, Imperial, RAL PPD |

2.2	Excludes

See responsibility column above.

3	DELIVERABLES

| Item | Responsibility |
| --- | --- |
| ASIC1 Design to agreed specification | RAL Technology |
| ASIC1 Common test & evaluation system (DAQ) | Imperial, RAL Technology |
| ASIC1 Radioactive source test system (hardware) | Imperial |
| ASIC1 Cosmics evaluation system (hardware) | Birmingham |
| ASIC1 Testing report | RAL Technology, Birmingham, Imperial, RAL PPD |
| ASIC2 Design to agreed specification | RAL Technology |
| ASIC2 Common test & evaluation system (DAQ) | Imperial, RAL Technology |
| ASIC2 Radioactive source test system (hardware) | Imperial |
| ASIC2 Cosmics evaluation system (hardware) | Birmingham |
| ASIC2 Beam test system & DAQ | Birmingham, Imperial, RAL PPD |
| ASIC2 Testing report | RAL Technology, Birmingham, Imperial, RAL PPD |

4	CONSTRAINTS

4.1	Budget

Please refer to the Financial Summary sheet that accompanies this document set

4.2	Schedule

- Feasibility study - continuing until end Apr 06

- First design - Start May 06 to end Dec 06

- First fabrication - Start Jan 07 to end Apr 07

- First basic tests - Start May 07 to end Jun 07

- First detailed tests - Start Jun 07 to end Mar 08

- Second design - Start Jul 07 to end Dec 07

- Second fabrication - Start Jan 08 to end Apr 08

- Second basic tests - Start May 08 to end Jun 08

- Second detailed tests - Start Jun 08 to end Mar 09

- Beam test PCB design and fabrication - Start Oct 07 to end Sep 08

- Beam test period - Start Oct 08 to end Mar 09

4.3	Performance

Evaluation of ASIC devices consists of “basic tests” and “detailed tests”, and is documented in the Testing Specification document.

4.4	Regulatory

None

5	IPR AND CONFIDENTIALITY

The Technology Business Unit (TBU) owns the design databases it has produced. TBU will procure any production tools such as masks or photo-tools, derived from these databases. None of these items will be released unless the appropriate protective agreements are in place.

Aspects of the “OPIC intelligent pixel” design from which some circuits for this project may be derived have been filed for patent protection in the UK.  Application number 0412296.6 dated June 02 2004.

6	PROJECT MONITORING

The RAL Technology responsibilities of this project will be managed using the online PMFS system, by J. Crooks.

Aspects of this project that are not assigned to RAL Technology are not managed using the online PMFS system, and will be managed by those organisations to which they are assigned in accordance with the processes and procedures in place as appropriate.