Risk Register & Control Report

| Project Name | Tera-Pixel APS for CALICE | Progress Date | 28/4/08 |
| --- | --- | --- | --- |

| Risk No. | # Description | Probability | Impact | Mitigation Strategy | Previous Status | Current Status | Date Closed | Risk Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Access to technology throughout the 3-year grant | Possible | Major problem | Discuss with foundry a deal for the two runs |  | Amber |  | RT |
| 1b | Supplementary note: Foundry availability (see file) | Possible | Major problem | Identify secondary option from Tender exercise  extra costs associated is likely to prevent original plan of two manufacturing runs. |  | Amber |  | JC |
| 2 | Error in design | Possible | Major problem | Thorough check of design before submission to foundry. Intermediate design reviews as set out in project management plan. |  | Green |  | JC |
| 3 | Error in CMOS processing | Rare | Major problem | Choose state-of-art foundry. Mitigate risk through firm contract so foundry pays for repeat run as soon as possible |  | Green |  | Foundry subcontractor |
| 4 | Test failure/delay | Possible | Major problem | Start preparing test not later than chip submission. Agreement of test specification document at PDR. |  | Green |  | PD/RT/MT/NW |
| 5 | Personnel leaving | Possible | Major problem | Provide support, good working environment and career prospects. Ensure adequate documentation of progress and direction to minimise disruption to project in event of personnel leaving. |  | Green |  | PD/RT/MT/NW |
| 6 | Error in specifications | Possible | Moderate | Invite external reviewers to PDR. Ensure adequate time between publishing documents and holding PDR for all concerned to fully read and query documents. |  | Green |  | JC |
| 7 | Budget overrun | Possible | Moderate | Costs dominated by sensor fabrication; negotiate cost for both runs from start to ensure total within budget. Keep other costs regularly reviewed |  | Amber |  | PD/RT |
| 7b | Budget cuts | Possible | Major problem | Has already happened (not foreseen!) resulting in change to project plan: Funding is now agreed for the continuation/conclusion of the project. | (new) | Green |  | PD |

Ratings: 	Low 	Medium 	High 	VHigh

Probability:	rare	possible	likely	almost certain

Impact:	minor 	moderate 	major problem	catastrophe

Risk status: Red = Active & impacting project; Amber = Active but contained without impact to cost & schedule; Green = not yet active.