## Close Out Report and Post Implementation Review

|  |  |  |  |
| --- | --- | --- | --- |
| **Project** **Name** | MAPS for CALICE (WP3) | **Date** | 7/10/09 |
| **Project Manager** | Jamie Crooks | **Division** | Detectors |

|  |  |  |  |
| --- | --- | --- | --- |
| Summary of performance against major milestones | | | |
| **Milestone** | **Planned Date** | **Date Complete** | **Comment** |

|  |  |  |  |
| --- | --- | --- | --- |
| TPAC1 IDR | 4-10-06 | 19-12-06 | Initial feasibility stage took longer than expected, as initial specs proved difficult to meet. |
| TPAC1 Submission | 21-01-07 | 30-4-07 | The January shuttle was aborted in the meeting of 20th Oct 2006, in which the then current pixel design was rejected for having too high noise, and the timing spec was relaxed from 140ns to 600ns to prioritise the noise spec.  The later submission deadline also allowed for the new Deep P-Well implant to be paid-for, developed and available on the April submission. |
| TPAC1 Proof of life | 30-8-07 | 29-9-09 | Some minor bugs took more time than foreseen to resolve/workaround |
| TPAC1 (working) delivered to collaborating institutes | 15-10-07 | 2-12-07 | Then used for DESY beam test in Dec 07 |
| TPAC2 PDR | Jul-07 | Aborted | TPAC2 was aborted when STFC suspended funding for this ILC project in Dec 07.  The remaining funds permitted more thorough testing of TPAC1, analysis of beam test results, and another multi-project submission (TPAC1.1) |
| TPAC2 Submission | Jan-08 |
| *The project plan was significantly revised in April 2008 to reflect the changes in funding. The milestones below were defined in Project Specification doc v1.2* |  |  |  |
| TPAC1.1 Design work starts (PDR) | May-08 | 1-5-08 |  |
| TPAC1.1 Submission (FDR) | Jul-08 | 18-7-08 |  |
| TPAC1.1 Basic tests | Dec-08 | Feb-09 | Significant problems with yield: Approx 50% of devices had power-ground short. Devices had to be probed & selected for bonding. Underlying cause was never understood, although subsequent TPAC1.2 devices never showed the same problem.  Intermittent bonding problems required further investigation.  A design error found that caused the pixel to oscillate at low thresholds due to small parasitic capacitance. |
| TPAC1.1 Detailed tests | Mar-09 | Aborted | The design error meant that the TPAC1.1 devices were not usable for detailed tests with source/beam. |
| TPAC1.2 Submission | end of FY08/09 | 3-3-09 | 2-Mask change re-spin of TPAC1.1 to fix pixel parasitic capacitance bug  (CfI funded) |
| *The testing of TPAC1.2 then fell under the new SPiDeR project, and as such there were no TPAC1.2 testing milestones defined in this project. The information below for reference/conclusion.* |  |  |  |
| TPAC1.2 Detailed tests |  | Aug-09 | Pixel bug was seen to be fixed by the mask change – devices working well.  Beam test at CERN shows promising data. |
|  |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Summary of financial information at close out** | | | | |
|  | **Staff (SY)** | **Staff (£k)** | **Recurrent £k** | **Total (£k)** |
| Planned Total Cost |  |  |  |  |
| Actual Total Cost |  |  |  |  |
| Agreed Income |  |  |  |  |
| Actual Income |  |  |  |  |

|  |
| --- |
| **Comments on the Financial Information** |
|  |

|  |  |
| --- | --- |
| **Project Close Out** | |
| **TECHNICAL:**  Final deliverables accepted  Any outstanding tasks listed  Any maintenance documentation complete  Technical documentation archived | Yes  Testing of TPAC1.2 under SPiDeR project  -  Copies held on CALICE project web pages and at RAL on medProj/CALICE/TPAC1.1\_resources |
| **LOGISTICAL:**  Any equipment returned  Any excess materials disposed of  Any dedicated space released | No, due to continuation of testing under SPiDeR  -  - |
| **PLANNING:**  Problem Reports cleared  Project Records archived | Problem reports 1,2,3,4,5 from TPAC1 were addressed in the design of TPAC1.1  Problem reports 1,3 from TPAC1.1 were addressed in the design of TPAC1.2  Problem report 2,4,5 from TPAC1.1 are still active and will feed into any related design in the SPiDeR project.  Project monitor system and project directory on medShr hold all relevant materials. |
| **FINANCIAL:**  Final payments made to suppliers  Project Codes closed  Final costs agreed | Yes  Yes |

|  |  |
| --- | --- |
| Assessment of the project | |
| **DELIVERABLES**  Where the deliverables adequately specified?  Did the deliverables meet the specification? | Yes  Partially  Serious design error was fixed by additional funding to make TPAC1.2 which then did essentially meet the specification.  Power consumption does not meet the original specification – this has been known and expected since the very first PDR. |
| **COSTS**  Were the deliverables produced within the agreed costs?  Was any contingency reserve used?  Was any management reserve used? | Development of Deep P-Well directly benefitted this project; some contingency was used for this, with top-up funding from CfI. |
| **TIMESCALES**  Were the deliverables produced within the agreed timescales?  Were the project planning techniques used sufficient? | Slip in TPAC1 submission schedule was agreed at the time to allow for Deep P-Well to be developed, and the pixel design to be refined.  The delayed submission of TPAC1 and the extra time spent delivering a working TPAC1 system would probably have delayed the start of TPAC2 by ~6 months if the project had continued to run as funded  Yes – A more significant problem was simple lack of information to allow adequate planning – the STFC funding cut took many months to be defined (when it would take effect, how much of the original grant could be still available) . This was then followed by an appeal for further funding with several more months of uncertainty. |
| **MONITORING**  Was monitoring sufficient for the control of the project?  Did the monitoring meet the customers needs? | Yes  Yes – monthly meetings with customer/collaborators throughout. |
| **REVIEWS**  Were the project reviews sufficient in number and scope?  Did the reviews meet the customers needs? | Yes  Yes |
| **STAKEHOLDER PLANS**  Did the Stakeholder Plan cover all the stakeholder issues?  Was the plan implemented effectively? | Yes  Updated STFC’s desires when ILC was officially “dropped” from UK roadmap. |
| **RISK MANAGEMENT PLAN**  Did the Risk Management Plan predict all the risks that affected the project?  Was the plan implemented effectively?  **TRAINING**  Where any training needs of the staff identified?  Was the training undertaken? | No – did not foresee STFC suspending funding of an approved grant mid-way through.  Yes  No  - |
| **MANAGEMENT**  Did the project manager receive the right amount of support from the team?  Did the team get the leadership it required? | Yes  - |
| **PROCUREMENT**  Were there any problems with procurement or subcontracting? | No |
| **CAE AND EQUIPMENT**  Were there any problems with the availability or performance of CAE systems or any equipment? | No |
| **SAFETY**  Did any safety issues arise? | No |
| **DEPARTMENT OBJECTIVES**  Did the project contribute to the wider objectives of the Department? | Yes  DPW developed & demonstrated, will be used for other projects  Development of staff, design experience & IP blocks that will be re-used in other current/future projects |
| **PROJECT PROCESS**  Have any improvements to the EID project process been identified? | - |
| **COMMENTS**  Any other comments? |  |

|  |
| --- |
| **Customer views on the project** |
|  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Approval by Project Manager** |  | **Date** |  |
| **Approval by Customer** |  | **Date** |  |