## Total
Total | Approved | Spend to end September 2006 |  | Latest estimate of future requirement (4) |  |  | Total |  | Variance
| (excluding contingency) | Actual | projected |  |  |  | Actual (2+4) | projected (3+4) | Actual (2-3) | projected (5-1)
| (1) | (2) | (3) | 2006/7 | 2007/8 | 2008/9 | (5) | (6)
Birmingham Effort | 162.29 | 26.8478 | 39.6078 | 20.4678 | 59.6112 | 58.3947 | 165.3215 | 178.0815 | -12.76 | 3.0315
Cambridge Effort | 250.52 | 98.1935 | 98.1827 | 37.5315 | 89.2172 | 25.3131 | 250.2553 | 250.2444 | 0.010816 | -0.26475
ICL Effort | 282.57 | 54.1902 | 58.0093 | 30.2702 | 108.937 | 89.8054 | 283.2027 | 287.0218 | -3.8191 | 0.63271
Manchester Effort | 216.51 | 53.6452 | 53.6369 | 20.7452 | 72.1987 | 69.9065 | 216.4957 | 216.4874 | 0.008275 | -0.01428
RHUL Effort | 237.64 | 29.6955 | 28.9772 | 32.7105 | 103.488 | 129.115 | 295.0089 | 294.2907 | 0.71825 | 57.3689
UCL Effort | 318.84 | 50.7666 | 85.7851 | 24.9066 | 116.1389 | 69.299 | 261.111 | 296.1296 | -35.0185 | -57.729
University Sub-Total1 | 1468.37 | 313.3387 | 364.199 | 166.6317 | 549.591 | 441.8337 | 1471.3951 | 1522.2554 | -50.8603 | 3.0251
RAL PPD Effort | 289 | 59.0363 | 59.0363 | 20.0362 | 103.5302 | 106.3734 | 288.9761 | 288.9761 | 0 | -0.02386
RAL ED/ID Effort | 277.2 | 64.128 | 70.1789 | 36.168 | 89.9501 | 87 | 277.2461 | 283.297 | -6.0509 | 0.04608
Equipment1 | 344.2 | 8.1 | 27.6667 | 42.9 | 151.1 | 142.1 | 344.2 | 363.7667 | -19.5667 | 0
Travel | 221.9 | 45 | 82.5833 | 58.6583 | 59.9 | 58.3 | 221.8583 | 259.4417 | -37.5833 | -0.041667
Consumables 1 | 103.5 | 6.1 | 21.125 | 26.4 | 20.2 | 50.8 | 103.5 | 118.525 | -15.025 | 0
Exceptional1
Total (excluding VAT and WA) | 2704.17 | 495.703 | 586.073 | 350.7943 | 974.2713 | 886.4071 | 2701.1757 | 2791.5457 | -90.37 | -2.9943
Working allowance | (1): 166.1 | 0 | -166.1
VAT
Total (including VAT & WA) | 2870.27 | 495.703 | 586.073 | 350.7943 | 974.2713 | 880.4071 | 2701.1757 | 2791.5457 | -90.37 | -169.0943
Contingency (held by PPARC) | (1): 152
Total Award | (1): 3022.27
1 Excluding Working Allowance and VAT

## WP1
WP1 | Approved | Spend to end September 2006 |  | Latest estimate of future requirement (4) |  |  | Total |  | Variance
| (excluding contingency) | Actual | projected |  |  |  | Actual (2+4) | projected (3+4) | Actual (2-3) | projected (5-1)
| (1) | (2) | (3) | 2006/7 | 2007/8 | 2008/9 | (5) | (6)
Birmingham Effort | 9.79 | 4.8956 | 8.0856 | 1.7057 | 0 | 0 | 6.6013 | 9.7913 | -3.19 | -3.1887
Cambridge Effort | 65.35 | 53.8897 | 53.8897 | 11.4577 | 0 | 0 | 65.3473 | 65.3473 | 0 | -0.002695
ICL Effort | 51.94 | 33.9124 | 37.7187 | 9.9924 | 8.448 | 0 | 52.3529 | 56.1591 | -3.8063 | 0.41288
Manchester Effort
RHUL Effort | 9.94 | 7.3688 | 7.3718 | 2.5688 | 0 | 0 | 9.9375 | 9.9406 | -0.003055 | -0.0025
UCL Effort | 38.63 | 8.7741 | 28.7053 | 2.3941 | 0 | 0 | 11.1682 | 31.0994 | -19.9312 | -27.4618
University Sub-Total1 | 175.65 | 108.8406 | 135.7711 | 28.1186 | 8.448 | 0 | 145.4071 | 172.3377 | -26.9306 | -30.2429
RAL PPD Effort
RAL ED/ID Effort
Equipment1
Travel | 111.7 | 31.1 | 57.0417 | 32.2583 | 22.4 | 25.9 | 111.6583 | 137.6 | -25.9417 | -0.041667
Consumables 1 | 11.1 | 4.9 | 7.5417 | 6.2 | 0 | 0 | 11.1 | 13.7417 | -2.6417 | 0
Exceptional1
Total (excluding VAT and WA) | 298.45 | 144.8406 | 194.4098 | 66.5769 | 30.848 | 25.9 | 268.1655 | 317.7347 | -49.5692 | -30.2845
Working allowance | (1): 21; (5): 0; (6): 0 | 0 | -21
VAT
Total (including VAT & WA) | 319.45 | 144.8406 | 194.4098 | 66.5769 | 30.848 | 25.9 | 268.1655 | 317.7347 | -49.5692 | -51.2845
Contingency (held by PPARC) | (1): 28.6
Total Award | (1): 348.05
1 Excluding Working Allowance and VAT

## WP2
WP2 | Approved | Spend to end September 2006 |  | Latest estimate of future requirement (4) |  |  | Total |  | Variance
| (excluding contingency) | Actual | projected |  |  |  | Actual (2+4) | projected (3+4) | Actual (2-3) | projected (5-1)
| (1) | (2) | (3) | 2006/7 | 2007/8 | 2008/9 | (5) | (6)
Birmingham Effort
Cambridge Effort | 113.31 | 32.8462 | 32.8354 | 14.6162 | 40.2653 | 25.3131 | 113.0407 | 113.0299 | 0.010816 | -0.2693
ICL Effort | 90.43 | 8.2868 | 8.2873 | 8.2868 | 42.7574 | 31.0852 | 90.4163 | 90.4168 | -0.00051375 | -0.013735
Manchester Effort | 64.41 | 21.3165 | 21.3124 | 9.3965 | 19.7894 | 13.9097 | 64.4121 | 64.4081 | 0.004055 | 0.002115
RHUL Effort | 103.9 | 14.958 | 14.2336 | 20.175 | 48.3014 | 70.3948 | 153.8292 | 153.1048 | 0.72436 | 49.9292
UCL Effort | 243.31 | 41.9925 | 55.1959 | 22.5125 | 95.9165 | 56.4091 | 216.8307 | 230.0341 | -13.2034 | -26.4793
University Sub-Total1 | 615.36 | 119.4 | 131.8646 | 74.9869 | 247.0301 | 197.112 | 638.5289 | 650.9936 | -12.4647 | 23.1689
RAL PPD Effort
RAL ED/ID Effort
Equipment1 | 118.1 | 8.1 | 26.4167 | 39.9 | 54.1 | 16 | 118.1 | 136.4167 | -18.3167 | 0
Travel | 24.9 | 4.6 | 8.5 | 7.4 | 9.9 | 3 | 24.9 | 28.8 | -3.9 | 0
Consumables 1 | 19.6 | 0 | 7.875 | 13.3 | 6.3 | 0 | 19.6 | 27.475 | -7.875 | 0
Exceptional1
Total (excluding VAT and WA) | 777.96 | 132.1 | 161.9302 | 135.587 | 317.3301 | 216.112 | 801.1289 | 830.9592 | -29.8302 | 23.1689
Working allowance | (1): 52.5; (5): 0; (6): 0 | 0 | -52.5
VAT
Total (including VAT & WA) | 830.46 | 132.1 | 161.9302 | 135.587 | 317.3301 | 216.112 | 801.1289 | 830.9592 | -29.8302 | -29.3311
Contingency (held by PPARC) | (1): 29.1
Total Award | (1): 859.56
1 Excluding Working Allowance and VAT

## WP3
WP3 | Approved | Spend to end September 2006 |  | Latest estimate of future requirement (4) |  |  | Total |  | Variance
| (excluding contingency) | Actual | projected |  |  |  | Actual (2+4) | projected (3+4) | Actual (2-3) | projected (5-1)
| (1) | (2) | (3) | 2006/7 | 2007/8 | 2008/9 | (5) | (6)
Birmingham Effort | 60.2 | 3.4113 | 3.4113 | 3.4113 | 26.4422 | 30.9008 | 64.1656 | 64.1656 | 0 | 3.9656
Cambridge Effort
ICL Effort | 111.1 | 5.9955 | 6.0016 | 5.9955 | 45.0595 | 54.2717 | 111.3221 | 111.3283 | -0.006165 | 0.22214
Manchester Effort
RHUL Effort
UCL Effort
University Sub-Total1 | 171.3 | 9.4068 | 9.4129 | 9.4068 | 71.5018 | 85.1725 | 175.4878 | 175.494 | -0.006165 | 4.1878
RAL PPD Effort | 289 | 59.0363 | 59.0363 | 20.0362 | 103.5302 | 106.3734 | 288.9761 | 288.9761 | 0 | -0.02386
RAL ED/ID Effort | 277.2 | 64.128 | 70.1789 | 36.168 | 89.9501 | 81 | 271.2461 | 277.297 | -6.0509 | -5.9539
Equipment1 | 206.6 | 0 | 1.25 | 3 | 94.8 | 108.8 | 206.6 | 207.85 | -1.25 | 0
Travel | 30.9 | 1.7 | 3.2083 | 4.6 | 7.3 | 17.3 | 30.9 | 32.4083 | -1.5083 | 0
Consumables 1 | 59.2 | 1.2 | 2.4167 | 1.8 | 9.6 | 46.6 | 59.2 | 60.4167 | -1.2167 | 0
Exceptional1
Total (excluding VAT and WA) | 1034.2 | 135.471 | 133.5586 | 75.011 | 376.6821 | 445.2459 | 1032.41 | 1030.4976 | 1.9124 | -1.79
Working allowance | (1): 60.7; (5): 0; (6): 0 | 0 | -60.7
VAT
Total (including VAT & WA) | 1094.9 | 135.471 | 133.5586 | 75.011 | 376.6821 | 445.2459 | 1032.41 | 1030.4976 | 1.9124 | -62.49
Contingency (held by PPARC) | (1): 86.9
Total Award | (1): 1181.8
1 Excluding Working Allowance and VAT

## WP4
WP4 | Approved | Spend to end September 2006 |  | Latest estimate of future requirement (4) |  |  | Total |  | Variance
| (excluding contingency) | Actual | projected |  |  |  | Actual (2+4) | projected (3+4) | Actual (2-3) | projected (5-1)
| (1) | (2) | (3) | 2006/7 | 2007/8 | 2008/9 | (5) | (6)
Birmingham Effort
Cambridge Effort
ICL Effort
Manchester Effort | 152.1 | 32.3287 | 32.3245 | 11.3487 | 52.4093 | 55.9969 | 152.0836 | 152.0794 | 0.00422 | -0.016395
RHUL Effort
UCL Effort
University Sub-Total1 | 152.1 | 32.3287 | 32.3245 | 11.3487 | 52.4093 | 55.9969 | 152.0836 | 152.0794 | 0.00422 | -0.016395
RAL PPD Effort
RAL ED/ID Effort
Equipment1 | 19.5 | 0 | 0 | 0 | 2.2 | 17.3 | 19.5 | 19.5 | 0 | 0
Travel | 4.2 | 0.8 | 1.4167 | 1.2 | 1.1 | 1.1 | 4.2 | 4.8167 | -0.61667 | 0
Consumables 1 | 9.5 | 0 | 1.2917 | 3.1 | 2.2 | 4.2 | 9.5 | 10.7917 | -1.2917 | 0
Exceptional1
Total (excluding VAT and WA) | 185.3 | 33.1287 | 33.1428 | 15.6487 | 57.9093 | 78.5969 | 185.2836 | 185.2976 | -0.014027 | -0.016395
Working allowance | (1): 10.8; (5): 0; (6): 0 | 0 | -10.8
VAT
Total (including VAT & WA) | 196.1 | 33.1287 | 33.1428 | 15.6487 | 57.9093 | 78.5969 | 185.2836 | 185.2976 | -0.014027 | -10.8164
Contingency (held by PPARC) | (1): 2.2
Total Award | (1): 198.3
1 Excluding Working Allowance and VAT

## WP5
WP5 | Approved | Spend to end September 2006 |  | Latest estimate of future requirement (4) |  |  | Total |  | Variance
| (excluding contingency) | Actual | projected |  |  |  | Actual (2+4) | projected (3+4) | Actual (2-3) | projected (5-1)
| (1) | (2) | (3) | 2006/7 | 2007/8 | 2008/9 | (5) | (6)
Birmingham Effort | 92.3 | 18.5408 | 28.1108 | 15.3508 | 33.169 | 27.4939 | 94.5546 | 104.1246 | -9.57 | 2.2546
Cambridge Effort | 71.86 | 11.4577 | 11.4577 | 11.4577 | 48.9519 | 0 | 71.8672 | 71.8672 | 0 | 0.007241
ICL Effort | 29.1 | 5.9955 | 6.0016 | 5.9955 | 12.672 | 4.4485 | 29.1114 | 29.1176 | -0.006165 | 0.011425
Manchester Effort
RHUL Effort | 123.8 | 7.3688 | 7.3718 | 9.9667 | 55.1866 | 58.7202 | 131.2423 | 131.2453 | -0.003055 | 7.4423
UCL Effort | 36.9 | 0 | 1.8839 | 0 | 20.2224 | 12.8898 | 33.1122 | 34.9961 | -1.8839 | -3.7878
University Sub-Total1 | 353.96 | 43.3627 | 54.8259 | 42.7707 | 170.2019 | 103.5524 | 359.8877 | 371.3508 | -11.4631 | 5.9277
RAL PPD Effort
RAL ED/ID Effort
Equipment1
Travel | 50.2 | 6.8 | 12.4167 | 13.2 | 19.2 | 11 | 50.2 | 55.8167 | -5.6167 | 0
Consumables 1 | 4.1 | 0 | 2 | 2 | 2.1 | 0 | 4.1 | 6.1 | -2 | 0
Exceptional1
Total (excluding VAT and WA) | 408.26 | 50.1627 | 63.0317 | 57.9707 | 191.5019 | 114.5524 | 414.1877 | 427.0567 | -12.869 | 5.9277
Working allowance | (1): 21.1; (5): 0; (6): 0 | 0 | -21.1
VAT
Total (including VAT & WA) | 429.36 | 50.1627 | 63.0317 | 57.9707 | 191.5019 | 114.5524 | 414.1877 | 427.0567 | -12.869 | -15.1723
Contingency (held by PPARC) | (1): 5.2
Total Award | (1): 434.56
1 Excluding Working Allowance and VAT

## Birmingham
Birmingham
Mikami | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 3.19 | 3.19 | 3.4113 | 3.32 | 3.6854 | 3.49 | 3.9277 | 3.62
WP1 months | 1 | 3.19 | 1 | 3.4113 |  | 0 |  | 0 | 2 | 6.6013 | 1.5 | 4.8956 | 0.5 | 1.7057
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 | 2 | 6.8226 | 3 | 11.0563 | 3 | 11.7831 | 8 | 29.662 | 1 | 3.4113 | 1 | 3.4113
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months | 1 | 3.19 | 9 | 30.7017 | 9 | 33.169 | 7 | 27.4939 | 26 | 94.5546 | 5.5 | 18.5408 | 4.5 | 15.3508
Staley | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.84 | 5.84 | 6.0006 | 5.84 | 6.167 | 5.84 | 6.3364 | 5.84
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 2 | 12.3341 | 2 | 12.6728 | 4 | 25.0069 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electronics techs | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.72 | 2.72 | 2.877 | 2.8 | 3.0518 | 2.89 | 3.2224 | 2.97
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 1 | 3.0518 | 2 | 6.4449 | 3 | 9.4967 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1 | 3.19 | 1 | 3.4113 | 0 | 0 | 0 | 0 | 2 | 6.6013 | 1.5 | 4.8956 | 0.5 | 1.7057
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 2 | 6.8226 | 6 | 26.4422 | 7 | 30.9008 | 15 | 64.1656 | 1 | 3.4113 | 1 | 3.4113
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 1 | 3.19 | 9 | 30.7017 | 9 | 33.169 | 7 | 27.4939 | 26 | 94.5546 | 5.5 | 18.5408 | 4.5 | 15.3508
Sum | 2 | 6.38 | 12 | 40.9356 | 15 | 59.6112 | 14 | 58.3947 | 43 | 165.3215 | 8 | 26.8478 | 6 | 20.4678
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Cambridge
Cambridge
Mavromanolakis | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 3.536 | 3.536 | 3.8192 | 3.717 | 4.0793 | 3.863 | 4.3867 | 4.043
WP1 months | 12 | 42.432 | 6 | 22.9153 |  | 0 |  | 0 | 18 | 65.3473 | 15 | 53.8897 | 3 | 11.4577
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 6 | 22.9153 | 12 | 48.9519 |  | 0 | 18 | 71.8672 | 3 | 11.4577 | 3 | 11.4577
Goodrick | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.77 | 5.77 | 5.9287 | 5.77 | 6.241 | 5.91 | 6.4123 | 5.91
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 2 | 11.54 | 2 | 11.8574 | 3 | 18.7229 | 1 | 6.4123 | 8 | 48.5326 | 3 | 17.4687 | 1 | 5.9287
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shaw | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.5 | 3.5 | 3.7093 | 3.61 | 3.865 | 3.66 | 4.0796 | 3.76
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.5 | 2 | 7.4185 | 2 | 7.7299 | 2 | 8.1592 | 7 | 26.8077 | 2 | 7.2093 | 1 | 3.7093
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Barham | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.19 | 3.19 | 3.3188 | 3.23 | 3.4531 | 3.27 | 3.5805 | 3.3
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.19 | 3 | 9.9565 | 4 | 13.8125 | 3 | 10.7415 | 11 | 37.7005 | 2.5 | 8.1682 | 1.5 | 4.9782
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 12 | 42.432 | 6 | 22.9153 | 0 | 0 | 0 | 0 | 18 | 65.3473 | 15 | 53.8897 | 3 | 11.4577
WP2 | 4 | 18.23 | 7 | 29.2324 | 9 | 40.2653 | 6 | 25.3131 | 26 | 113.0407 | 7.5 | 32.8462 | 3.5 | 14.6162
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 6 | 22.9153 | 12 | 48.9519 | 0 | 0 | 18 | 71.8672 | 3 | 11.4577 | 3 | 11.4577
Sum | 16 | 60.662 | 19 | 75.063 | 21 | 89.2172 | 6 | 25.3131 | 62 | 250.2553 | 25.5 | 98.1935 | 9.5 | 37.5315
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## ICL
ICL
Magnan | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 3.79 | 3.79 | 3.997 | 3.89 | 4.224 | 4 | 4.4485 | 4.1
WP1 months | 5 | 18.95 | 5 | 19.9849 | 2 | 8.448 |  | 0 | 12 | 47.3829 | 7.5 | 28.9424 | 2.5 | 9.9924
WP2 months |  | 0 | 1 | 3.997 | 2 | 8.448 | 2 | 8.897 | 5 | 21.342 | 0.5 | 1.9985 | 0.5 | 1.9985
WP3 months |  | 0 | 3 | 11.9909 | 5 | 21.12 | 4 | 17.794 | 12 | 50.9049 | 1.5 | 5.9955 | 1.5 | 5.9955
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 3 | 11.9909 | 3 | 12.672 | 1 | 4.4485 | 7 | 29.1114 | 1.5 | 5.9955 | 1.5 | 5.9955
Zorba | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.97 | 4.97 | 5.2505 | 5.11 | 5.544 | 5.25 | 5.8482 | 5.39
WP1 months | 1 | 4.97 |  | 0 |  | 0 |  | 0 | 1 | 4.97 | 1 | 4.97 | 0 | 0
WP2 months |  | 0 | 1 | 5.2505 | 2 | 11.088 | 1 | 5.8482 | 4 | 22.1867 | 0.5 | 2.6253 | 0.5 | 2.6253
WP3 months |  | 0 |  | 0 | 2 | 11.088 | 3 | 17.5445 | 5 | 28.6324 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Price | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6.93 | 6.93 | 7.3261 | 7.13 | 7.7405 | 7.33 | 8.17 | 7.53
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 1 | 7.3261 | 3 | 23.2214 | 2 | 16.3401 | 6 | 46.8876 | 0.5 | 3.663 | 0.5 | 3.663
WP3 months |  | 0 |  | 0 | 1 | 7.7405 | 1 | 8.17 | 2 | 15.9105 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Clark | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.58 | 4.58 | 4.8395 | 4.71 | 5.111 | 4.84 | 5.3816 | 4.96
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 1 | 5.111 | 2 | 10.7632 | 3 | 15.8742 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 6 | 23.92 | 5 | 19.9849 | 2 | 8.448 | 0 | 0 | 13 | 52.3529 | 8.5 | 33.9124 | 2.5 | 9.9924
WP2 | 0 | 0 | 3 | 16.5736 | 7 | 42.7574 | 5 | 31.0852 | 15 | 90.4163 | 1.5 | 8.2868 | 1.5 | 8.2868
WP3 | 0 | 0 | 3 | 11.9909 | 9 | 45.0595 | 10 | 54.2717 | 22 | 111.3221 | 1.5 | 5.9955 | 1.5 | 5.9955
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 3 | 11.9909 | 3 | 12.672 | 1 | 4.4485 | 7 | 29.1114 | 1.5 | 5.9955 | 1.5 | 5.9955
Sum | 6 | 23.92 | 14 | 60.5403 | 21 | 108.937 | 16 | 89.8054 | 57 | 283.2027 | 13 | 54.1902 | 7 | 30.2702
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Manchester
Manchester
Hughes-Jones | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 5.92 | 5.92 | 6.2369 | 6.07 | 6.5683 | 6.22 | 6.9115 | 6.37
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 5.92 | 2 | 12.4739 | 2 | 13.1366 | 1 | 6.9115 | 6 | 38.4419 | 2 | 12.1569 | 1 | 6.2369
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kolya | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6 | 6 | 6.3191 | 6.15 | 6.6528 | 6.3 | 6.9982 | 6.45
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 6 | 1 | 6.3191 | 1 | 6.6528 | 1 | 6.9982 | 4 | 25.9702 | 1.5 | 9.1596 | 0.5 | 3.1596
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thompson | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.92 | 5.92 | 6.2369 | 6.07 | 6.5683 | 6.22 | 6.9115 | 6.37
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 5.92 | 1 | 6.2369 | 4 | 26.2733 | 4 | 27.6458 | 10 | 66.076 | 1.5 | 9.0385 | 0.5 | 3.1185
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Snow | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums
Monthly cost | 5.73 | 5.73 | 6.2678 | 6.1 | 6.7373 | 6.38 | 7.3238 | 6.75
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 5.73 | 1 | 6.2678 | 1 | 6.7373 | 1 | 7.3238 | 4 | 26.0588 | 1.5 | 8.8639 | 0.5 | 3.1339
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Freestone | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4 | 4 | 4.3977 | 4.28 | 4.7942 | 4.54 | 5.2297 | 4.82
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 4 | 1 | 4.3977 | 2 | 9.5885 | 2 | 10.4594 | 6 | 28.4456 | 1.5 | 6.1989 | 0.5 | 2.1989
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elvin | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.94 | 2.94 | 3.1955 | 3.11 | 3.4954 | 3.31 | 3.7649 | 3.47
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 2.94 | 1 | 3.1955 | 2 | 6.9907 | 2 | 7.5299 | 6 | 20.6561 | 1.5 | 4.5378 | 0.5 | 1.5978
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perry | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.39 | 2.39 | 2.5996 | 2.53 | 2.8195 | 2.67 | 3.038 | 2.8
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 2.39 | 1 | 2.5996 | 1 | 2.8195 | 1 | 3.038 | 4 | 10.8471 | 1.5 | 3.6898 | 0.5 | 1.2998
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 2 | 11.92 | 3 | 18.793 | 3 | 19.7894 | 2 | 13.9097 | 10 | 64.4121 | 3.5 | 21.3165 | 1.5 | 9.3965
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 5 | 20.98 | 5 | 22.6975 | 10 | 52.4093 | 10 | 55.9969 | 30 | 152.0836 | 7.5 | 32.3287 | 2.5 | 11.3487
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 7 | 32.9 | 8 | 41.4905 | 13 | 72.1987 | 12 | 69.9065 | 40 | 216.4957 | 11 | 53.6452 | 4 | 20.7452
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RHUL
RHUL
New RA3 | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 3.5 | 3.5 | 3.699 | 3.6 | 3.8966 | 3.69 | 4.1121 | 3.79
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 3 | 11.097 | 6 | 23.3798 | 14 | 57.5701 | 23 | 92.0469 | 0 | 0 | 3 | 11.097
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 2 | 7.398 | 6 | 23.3798 | 6 | 24.6729 | 14 | 55.4507 | 0 | 0 | 2 | 7.398
Salvatore | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.8 | 4.8 | 5.1375 | 5 | 5.3011 | 5.02 | 5.6745 | 5.23
WP1 months | 1 | 4.8 | 1 | 5.1375 |  | 0 |  | 0 | 2 | 9.9375 | 1.5 | 7.3688 | 0.5 | 2.5688
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months | 1 | 4.8 | 1 | 5.1375 | 6 | 31.8067 | 6 | 34.0473 | 14 | 75.7915 | 1.5 | 7.3688 | 0.5 | 2.5688
Green | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.88 | 5.88 | 6.052 | 5.89 | 6.2304 | 5.9 | 6.4123 | 5.91
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 5.88 | 3 | 18.1559 | 4 | 24.9216 | 2 | 12.8247 | 10 | 61.7822 | 2.5 | 14.958 | 1.5 | 9.078
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1 | 4.8 | 1 | 5.1375 | 0 | 0 | 0 | 0 | 2 | 9.9375 | 1.5 | 7.3688 | 0.5 | 2.5688
WP2 | 1 | 5.88 | 6 | 29.2529 | 10 | 48.3014 | 16 | 70.3948 | 33 | 153.8292 | 2.5 | 14.958 | 4.5 | 20.175
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 1 | 4.8 | 3 | 12.5355 | 12 | 55.1866 | 12 | 58.7202 | 28 | 131.2423 | 1.5 | 7.3688 | 2.5 | 9.9667
Sum | 3 | 15.48 | 10 | 46.9259 | 22 | 103.488 | 28 | 129.115 | 63 | 295.0089 | 5.5 | 29.6955 | 7.5 | 32.7105
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## UCL
UCL
New RA4 | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 3.54 | 3.54 | 3.7709 | 3.67 | 4.0445 | 3.83 | 4.2966 | 3.96
WP1 months | 0.5 | 1.77 | 0 | 0 |  | 0 |  | 0 | 0.5 | 1.77 | 0.5 | 1.77 | 0 | 0
WP2 months |  | 0 | 0 | 0 | 7 | 28.3114 | 5 | 21.483 | 12 | 49.7944 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 0 | 0 | 5 | 20.2224 | 3 | 12.8898 | 8 | 33.1122 | 0 | 0 | 0 | 0
Warren | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.61 | 4.61 | 4.7881 | 4.66 | 5.2483 | 4.97 | 5.4576 | 5.03
WP1 months | 1 | 4.61 | 1 | 4.7881 |  | 0 |  | 0 | 2 | 9.3981 | 1.5 | 7.0041 | 0.5 | 2.3941
WP2 months | 2 | 9.22 | 5 | 23.9408 | 6 | 31.4899 | 3 | 16.3727 | 16 | 81.0233 | 4.5 | 21.1904 | 2.5 | 11.9704
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Postranecky | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.13 | 5.13 | 5.2711 | 5.13 | 6.0192 | 5.7 | 6.1845 | 5.7
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 2 | 10.26 | 4 | 21.0843 | 6 | 36.1152 | 3 | 18.5535 | 15 | 86.013 | 4 | 20.8022 | 2 | 10.5421
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1.5 | 6.38 | 1 | 4.7881 | 0 | 0 | 0 | 0 | 2.5 | 11.1682 | 2 | 8.7741 | 0.5 | 2.3941
WP2 | 4 | 19.48 | 9 | 45.0251 | 19 | 95.9165 | 11 | 56.4091 | 43 | 216.8307 | 8.5 | 41.9925 | 4.5 | 22.5125
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 5 | 20.2224 | 3 | 12.8898 | 8 | 33.1122 | 0 | 0 | 0 | 0
Sum | 5.5 | 25.86 | 10 | 49.8132 | 24 | 116.1389 | 14 | 69.299 | 53.5 | 261.111 | 10.5 | 50.7666 | 5 | 24.9066
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RAL PPD
RAL PPD
Tyndel | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 6.5 | 6.5 | 6.6787 | 6.5 | 6.864 | 6.5 | 7.0525 | 6.5
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 1 | 6.5 | 1 | 6.6787 | 1 | 6.864 | 1 | 7.0525 | 4 | 27.0953 | 1.5 | 9.8394 | 0.5 | 3.3394
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Villani | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6.5 | 6.5 | 6.6787 | 6.5 | 6.864 | 6.5 | 7.0525 | 6.5
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 5 | 32.5 | 5 | 33.3937 | 5 | 34.32 | 5 | 35.2625 | 20 | 135.4762 | 7.5 | 49.1969 | 2.5 | 16.6969
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
New RA5 | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.92 | 4.92 | 5.0553 | 4.92 | 5.1955 | 4.92 | 5.3382 | 4.92
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 12 | 62.3462 | 12 | 64.0584 | 24 | 126.4046 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 6 | 39 | 6 | 40.0725 | 18 | 103.5302 | 18 | 106.3734 | 48 | 288.9761 | 9 | 59.0363 | 3 | 20.0362
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 6 | 39 | 6 | 40.0725 | 18 | 103.5302 | 18 | 106.3734 | 48 | 288.9761 | 9 | 59.0363 | 3 | 20.0362
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RAL ID
RAL ID
Turchetta | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2006 |  | Rest of 2006/7
Monthly cost | 10.89 | 10.89 | 11.508 | 11.2 | 12.144 | 11.5 | 12.8247 | 11.82
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 1 | 10.89 | 1 | 11.508 | 1 | 12.144 | 1 | 12.8247 | 4 | 47.3667 | 1.5 | 16.644 | 0.5 | 5.754
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crooks | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.69 | 5.69 | 6.0828 | 5.92 | 6.4838 | 6.14 | 6.9006 | 6.36
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 3 | 17.07 | 10 | 60.828 | 12 | 77.8061 | 9 | 62.1054 | 34 | 217.8095 | 8 | 47.484 | 5 | 30.414
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 4 | 27.96 | 11 | 72.336 | 13 | 89.9501 | 10 | 74.9301 | 38 | 265.1762 | 9.5 | 64.128 | 5.5 | 36.168
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 4 | 27.96 | 11 | 72.336 | 13 | 89.9501 | 10 | 74.9301 | 38 | 265.1762 | 9.5 | 64.128 | 5.5 | 36.168
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085