## Total
Total | Approved | Transfers | Actual spend in previous years |  | Current year 2007/8 |  | Latest estimate of future requirement | Total |  | Variance
| (excluding contingency) |  | (2) |  | Actual spend to Sept 07 | Projected spend this year | (5) | Actual spend (2+3) | Projected spend (2+4+5) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | (3) | (4) | 2008/9 | (6) | (7)
Birmingham Effort | 162.29 | 0 | 6.3 | 43.7715 | 29.8056 | 59.6112 | 58.3947 | 79.8771 | 168.0774 | -82.4129 | 5.7874
Cambridge Effort | 250.52 | 0 | 57.687 | 76.165 | 44.6086 | 89.2172 | 25.3131 | 178.4606 | 248.3823 | -72.0594 | -2.1377
ICL Effort | 282.57 | 0 | 22.512 | 56.2126 | 54.4685 | 108.937 | 89.8054 | 133.1931 | 277.467 | -149.3769 | -5.103
Manchester Effort | 216.51 | 0 | 29.75 | 41.4391 | 36.0994 | 72.1987 | 69.9065 | 107.2884 | 213.2943 | -109.2216 | -3.2157
RHUL Effort | 237.64 | 57.7 | 15.25 | 37.704 | 51.744 | 103.488 | 133.2271 | 104.698 | 289.6692 | -190.642 | -5.6708
UCL Effort | 318.84 | -57.7 | 26.09 | 49.8132 | 58.0694 | 116.1389 | 69.299 | 133.9726 | 261.341 | -127.1674 | 0.20103
University Sub-Total1 | 1468.37 |  | 157.589 | 305.1054 | 274.7955 | 549.591 | 445.9459 | 737.4899 | 1458.2312 | -730.8801 | -10.1388
RAL PPD Effort | 289 | 0 | 11.54 | 53.61 | 52.15 | 103.5302 | 106.3734 | 117.3 | 275.0536 | -171.7 | -13.9464
RAL ED/ID Effort | 277.2 | 0 | 14.38 | 82.32 | 43.05 | 89.9501 | 81 | 139.75 | 267.6501 | -137.45 | -9.5499
Equipment1 | 344.2 | 15 | 0 | 23.221 | 58.8 | 130.11 | 205.869 | 82.021 | 359.2 | -277.179 | 0
Travel | 221.9 | 0 | 24.123 | 49.852 | 50.57 | 77.85 | 70.075 | 124.545 | 221.9 | -97.355 | 0
Consumables 1 | 103.5 | 0 | 1.635 | 17.8 | 8.89 | 20.06 | 64.005 | 28.325 | 103.5 | -75.175 | 0
Exceptional1
Total (excluding VAT and WA) | 2704.17 |  | 209.267 | 531.9084 | 488.2555 | 971.0913 | 973.2682 | 1229.4309 | 2678.9249 | -1489.7391 | -40.2451
Working allowance | 166.1 | -15 | [7 empty] | 0 | -151.1
VAT
Total (including VAT & WA) | 2870.27 |  | 209.267 | 531.9084 | 488.2555 | 971.0913 | 958.2682 | 1229.4309 | 2663.9249 | -1489.7391 | -191.3451
Contingency (held by STFC) | 152
Total Award | 3022.27
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP1
WP1 | Approved | Transfers | Actual spend in previous years |  | Current year 2007/8 |  | Latest estimate of future requirement | Total |  | Variance
| (excluding contingency) |  | (2) |  | Actual spend to Sept 07 | Projected spend this year | (5) | Actual spend (2+3) | Projected spend (2+4+5) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | (3) | (4) | 2008/9 | (6) | (7)
Birmingham Effort | 9.79 |  | 3.15 | 3.6476 | 0 | 0 | 0 | 6.7976 | 6.7976 | -2.9924 | -2.9924
Cambridge Effort | 65.35 |  | 39.502 | 23.11 | 0 | 0 | 0 | 62.612 | 62.612 | -2.738 | -2.738
ICL Effort | 51.94 |  | 22.512 | 18.182 | 4.224 | 8.448 | 0 | 44.918 | 49.142 | -7.022 | -2.798
Manchester Effort
RHUL Effort | 9.94 |  | 4.7 | 5 | 0 | 0 | 0 | 9.7 | 9.7 | -0.24 | -0.24
UCL Effort | 38.63 |  | 6.61 | 4.7881 | 0 | 0 | 0 | 11.3981 | 4.7881 | -27.2319 | -33.8419
University Sub-Total1 | 175.65 |  | 76.474 | 54.7278 | 4.224 | 8.448 | 0 | 135.4258 | 133.0398 | -40.2242 | -42.6102
RAL PPD Effort
RAL ED/ID Effort
Equipment1
Travel | 111.7 |  | 16.7384 | 34.0718 | 20.9 | 32.2 | 28.6898 | 71.7102 | 111.7 | -39.9898 | 0
Consumables 1 | 11.1 |  | 0.407 | 3.875 | 2.2 | 0 | 6.818 | 6.482 | 11.1 | -4.618 | 0
Exceptional1
Total (excluding VAT and WA) | 298.45 |  | 93.6194 | 92.6746 | 27.324 | 40.648 | 35.5078 | 213.618 | 255.8398 | -84.832 | -42.6102
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 298.45 |  | 93.6194 | 92.6746 | 27.324 | 40.648 | 35.5078 | 213.618 | 255.8398 | -84.832 | -42.6102
Contingency (held by STFC)
Total Award | 298.45
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP2
WP" | Approved | Transfers | Actual spend in previous years |  | Current year 2007/8 |  | Latest estimate of future requirement | Total |  | Variance
| (excluding contingency) |  | (2) |  | Actual spend to Sept 07 | Projected spend this year | (5) | Actual spend (2+3) | Projected spend (2+4+5) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | (3) | (4) | 2008/9 | (6) | (7)
Birmingham Effort
Cambridge Effort | 113.31 |  | 18.185 | 29.945 | 20.1326 | 40.2653 | 25.3131 | 68.2626 | 113.7083 | -45.0474 | 0.39833
ICL Effort | 90.43 |  | 0 | 16.2126 | 21.3787 | 42.7574 | 31.0852 | 37.5913 | 90.0553 | -52.8387 | -0.37471
Manchester Effort | 64.41 |  | 9.44 | 17.1901 | 9.8947 | 19.7894 | 13.9097 | 36.5248 | 60.3292 | -27.8852 | -4.0808
RHUL Effort | 103.9 | 57.7 | 5.85 | 22.867 | 24.1507 | 48.3014 | 74.507 | 52.8677 | 151.5254 | -108.7323 | -10.0746
UCL Effort | 243.31 | -57.7 | 19.48 | 45.0251 | 47.9582 | 95.9165 | 56.4091 | 112.4633 | 216.8307 | -73.1467 | 31.2207
University Sub-Total1 | 615.36 |  | 52.955 | 131.2397 | 123.515 | 247.0301 | 201.2241 | 307.7098 | 632.4489 | -307.6502 | 17.0889
RAL PPD Effort
RAL ED/ID Effort
Equipment1 | 118.1 |  | 0 | 8.114 | 24 | 65 | 44.986 | 32.114 | 118.1 | -85.986 | 0
Travel | 24.9 |  | 2.9538 | 3.7885 | 6.17 | 9.5 | 8.6577 | 12.9123 | 24.9 | -11.9877 | 0
Consumables 1 | 19.6 |  | 0 | 13.908 | 1.69 | 6.34 | -0.648 | 15.598 | 19.6 | -4.002 | 0
Exceptional1
Total (excluding VAT and WA) | 777.96 |  | 55.9088 | 157.0502 | 155.375 | 327.8701 | 254.2198 | 368.3341 | 795.0489 | -409.6259 | 17.0889
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 777.96 |  | 55.9088 | 157.0502 | 155.375 | 327.8701 | 254.2198 | 368.3341 | 795.0489 | -409.6259 | 17.0889
Contingency (held by STFC)
Total Award | 777.96
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP3
WP3 | Approved | Transfers | Actual spend in previous years |  | Current year 2007/8 |  | Latest estimate of future requirement | Total |  | Variance
| (excluding contingency) |  | (2) |  | Actual spend to Sept 07 | Projected spend this year | (5) | Actual spend (2+3) | Projected spend (2+4+5) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | (3) | (4) | 2008/9 | (6) | (7)
Birmingham Effort | 60.2 |  | 0 | 7.2953 | 13.2211 | 26.4422 | 30.9008 | 20.5164 | 64.6383 | -39.6836 | 4.4383
Cambridge Effort
ICL Effort | 111.1 |  | 0 | 10.909 | 22.5298 | 45.0595 | 54.2717 | 33.4388 | 110.2402 | -77.6612 | -0.85978
Manchester Effort
RHUL Effort
UCL Effort
University Sub-Total1 | 171.3 |  | 0 | 18.2042 | 35.7509 | 71.5018 | 85.1725 | 53.9551 | 174.8785 | -117.3449 | 3.5785
RAL PPD Effort | 289 |  | 11.54 | 53.61 | 52.15 | 103.5302 | 106.3734 | 117.3 | 275.0536 | -171.7 | -13.9464
RAL ED/ID Effort | 277.2 |  | 14.38 | 82.32 | 43.05 | 89.9501 | 81 | 139.75 | 267.6501 | -137.45 | -9.5499
Equipment1 | 206.6 | 15 | 0 | 15.107 | 34.8 | 63 | 143.493 | 49.907 | 221.6 | -171.693 | 0
Travel | 30.9 |  | 0.49231 | 3.156 | 4.9 | 7.39 | 19.8616 | 8.5484 | 30.9 | -22.3516 | 0
Consumables 1 | 59.2 |  | 1.228 | 0.017 | 5 | 9.5 | 48.455 | 6.245 | 59.2 | -52.955 | 0
Exceptional1
Total (excluding VAT and WA) | 1034.2 |  | 27.6403 | 172.4143 | 175.6509 | 344.8721 | 484.3555 | 375.7055 | 1029.2822 | -673.4945 | -19.9178
Working allowance |  | -15 |  |  |  |  | -15 | 0 | -15 | 15 | 0
VAT
Total (including VAT & WA) | 1034.2 |  | 27.6403 | 172.4143 | 175.6509 | 344.8721 | 469.3555 | 375.7055 | 1014.2822 | -658.4945 | -19.9178
Contingency (held by STFC)
Total Award | 1034.2
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP4
WP4 | Approved | Transfers | Actual spend in previous years |  | Current year 2007/8 |  | Latest estimate of future requirement | Total |  | Variance
| (excluding contingency) |  | (2) |  | Actual spend to Sept 07 | Projected spend this year | (5) | Actual spend (2+3) | Projected spend (2+4+5) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | (3) | (4) | 2008/9 | (6) | (7)
Birmingham Effort
Cambridge Effort
ICL Effort
Manchester Effort | 152.1 |  | 20.31 | 24.249 | 26.2046 | 52.4093 | 55.9969 | 70.7636 | 152.9651 | -81.3364 | 0.86513
RHUL Effort
UCL Effort
University Sub-Total1 | 152.1 |  | 20.31 | 24.249 | 26.2046 | 52.4093 | 55.9969 | 70.7636 | 152.9651 | -81.3364 | 0.86513
RAL PPD Effort
RAL ED/ID Effort
Equipment1 | 19.5 |  | 0 | 0 | 0 | 2.11 | 17.39 | 0 | 19.5 | -19.5 | 0
Travel | 4.2 |  | 0.49231 | 0.63244 | 0.6 | 1.06 | 2.0153 | 1.7247 | 4.2 | -2.4753 | 0
Consumables 1 | 9.5 |  | 0 | 0 | 0 | 2.11 | 7.39 | 0 | 9.5 | -9.5 | 0
Exceptional1
Total (excluding VAT and WA) | 185.3 |  | 20.8023 | 24.8814 | 26.8046 | 57.6893 | 82.7921 | 72.4884 | 186.1651 | -112.8116 | 0.86513
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 185.3 |  | 20.8023 | 24.8814 | 26.8046 | 57.6893 | 82.7921 | 72.4884 | 186.1651 | -112.8116 | 0.86513
Contingency (held by STFC)
Total Award | 185.3
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## WP5
WP5 | Approved | Transfers | Actual spend in previous years |  | Current year 2007/8 |  | Latest estimate of future requirement | Total |  | Variance
| (excluding contingency) |  | (2) |  | Actual spend to Sept 07 | Projected spend this year | (5) | Actual spend (2+3) | Projected spend (2+4+5) | Actual (6-1-1a) | Projected (7-1-1a)
| (1) | (1a) | 2005/6 | 2006/7 | (3) | (4) | 2008/9 | (6) | (7)
Birmingham Effort | 92.3 |  | 3.15 | 32.8286 | 16.5845 | 33.169 | 27.4939 | 52.5631 | 96.6415 | -39.7369 | 4.3415
Cambridge Effort | 71.86 |  | 0 | 23.11 | 24.476 | 48.9519 | 0 | 47.586 | 72.0619 | -24.274 | 0.20194
ICL Effort | 29.1 |  | 0 | 10.909 | 6.336 | 12.672 | 4.4485 | 17.245 | 28.0295 | -11.855 | -1.0705
Manchester Effort
RHUL Effort | 123.8 |  | 4.7 | 9.837 | 27.5933 | 55.1866 | 58.7202 | 42.1303 | 128.4438 | -81.6697 | 4.6438
UCL Effort | 36.9 |  | 0 | 0 | 10.1112 | 20.2224 | 12.8898 | 10.1112 | 33.1122 | -26.7888 | -3.7878
University Sub-Total1 | 353.96 |  | 7.85 | 76.6846 | 85.1009 | 170.2019 | 103.5524 | 169.6356 | 358.2889 | -184.3244 | 4.3289
RAL PPD Effort
RAL ED/ID Effort
Equipment1
Travel | 50.2 |  | 3.4461 | 8.2033 | 18 | 27.7 | 10.8506 | 29.6494 | 50.2 | -20.5506 | 0
Consumables 1 | 4.1 |  | 0 | 0 | 0 | 2.11 | 1.99 | 0 | 4.1 | -4.1 | 0
Exceptional1
Total (excluding VAT and WA) | 408.26 |  | 11.2961 | 84.8879 | 103.1009 | 200.0119 | 116.393 | 199.285 | 412.5889 | -208.975 | 4.3289
Working allowance | [7 empty] | 0 | 0 | 0 | 0
VAT
Total (including VAT & WA) | 408.26 |  | 11.2961 | 84.8879 | 103.1009 | 200.0119 | 116.393 | 199.285 | 412.5889 | -208.975 | 4.3289
Contingency (held by STFC)
Total Award | 408.26
1 Excluding Working Allowance and VAT
Use of columns:
(1) = The amount approved by STFC
(1a) = This column should be used to show any virements between headings, for example when Working Allowance is used, the amount should appear as a debit in the WA row and then credited to the relevant row
(2) = The actual spend in previous financial years, by year
(3) = The actual spend in the current financial year up to the most recent quarter
(4) = The total projected spend for the current financial year, including any expenditure so far (ie actual spend this year plus predictions of remaining spend this year)
(5) = Projected spend for the remaining year
(6) = The actual spend so far
(7) = Projected spend over the whole duration of the project (ie actual spend so far plus predictions of remaining spend to project completion)
The variance columns show the difference between the actual and projected amounts and the approved amount.

## Birmingham
Birmingham
Mikami | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.15 | 3.15 | 3.6476 | 3.55 | 3.6854 | 3.49 | 3.9277 | 3.62
WP1 months | 1 | 3.15 | 1 | 3.6476 |  | 0 |  | 0 | 2 | 6.7976 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 | 2 | 7.2953 | 3 | 11.0563 | 3 | 11.7831 | 8 | 30.1347 | 1.5 | 5.5282 | 4.5 | 17.3113
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months | 1 | 3.15 | 9 | 32.8286 | 9 | 33.169 | 7 | 27.4939 | 26 | 96.6415 | 4.5 | 16.5845 | 11.5 | 44.0784
Staley | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.84 | 5.84 | 6.0006 | 5.84 | 6.167 | 5.84 | 6.3364 | 5.84
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 2 | 12.3341 | 2 | 12.6728 | 4 | 25.0069 | 1 | 6.167 | 3 | 18.8398
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Electronics techs | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.72 | 2.72 | 2.877 | 2.8 | 3.0518 | 2.89 | 3.2224 | 2.97
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 1 | 3.0518 | 2 | 6.4449 | 3 | 9.4967 | 0.5 | 1.5259 | 2.5 | 7.9708
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1 | 3.15 | 1 | 3.6476 | 0 | 0 | 0 | 0 | 2 | 6.7976 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 0 | 0 | 2 | 7.2953 | 6 | 26.4422 | 7 | 30.9008 | 15 | 64.6383 | 3 | 13.2211 | 10 | 44.1219
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 1 | 3.15 | 9 | 32.8286 | 9 | 33.169 | 7 | 27.4939 | 26 | 96.6415 | 4.5 | 16.5845 | 11.5 | 44.0784
Sum | 2 | 6.3 | 12 | 43.7715 | 15 | 59.6112 | 14 | 58.3947 | 43 | 168.0774 | 7.5 | 29.8056 | 21.5 | 88.2003
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Cambridge
Cambridge
Mavromanolakis | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.536 | 3.536 | 3.8192 | 3.717 | 4.0793 | 3.863 | 4.3867 | 4.043
WP1 months | 12 | 39.502 | 6 | 23.11 |  | 0 |  | 0 | 18 | 62.612 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 6 | 23.11 | 12 | 48.9519 |  | 0 | 18 | 72.0619 | 6 | 24.476 | 6 | 24.476
Goodrick | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.77 | 5.77 | 5.9287 | 5.77 | 6.241 | 5.91 | 6.4123 | 5.91
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 2 | 11.425 | 2 | 12.16 | 3 | 18.7229 | 1 | 6.4123 | 8 | 48.7202 | 1.5 | 9.3614 | 2.5 | 15.7738
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shaw | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.5 | 3.5 | 3.7093 | 3.61 | 3.865 | 3.66 | 4.0796 | 3.76
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.583 | 2 | 7.566 | 2 | 7.7299 | 2 | 8.1592 | 7 | 27.0381 | 1 | 3.865 | 3 | 12.0242
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Barham | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.19 | 3.19 | 3.3188 | 3.23 | 3.4531 | 3.27 | 3.5805 | 3.3
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.177 | 3 | 10.219 | 4 | 13.8125 | 3 | 10.7415 | 11 | 37.95 | 2 | 6.9062 | 5 | 17.6477
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 12 | 39.502 | 6 | 23.11 | 0 | 0 | 0 | 0 | 18 | 62.612 | 0 | 0 | 0 | 0
WP2 | 4 | 18.185 | 7 | 29.945 | 9 | 40.2653 | 6 | 25.3131 | 26 | 113.7083 | 4.5 | 20.1326 | 10.5 | 45.4457
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 6 | 23.11 | 12 | 48.9519 | 0 | 0 | 18 | 72.0619 | 6 | 24.476 | 6 | 24.476
Sum | 16 | 57.687 | 19 | 76.165 | 21 | 89.2172 | 6 | 25.3131 | 62 | 248.3823 | 10.5 | 44.6086 | 16.5 | 69.9217
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## ICL
ICL
Magnan | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.79 | 3.79 | 3.997 | 3.89 | 4.224 | 4 | 4.4485 | 4.1
WP1 months | 5 | 17.542 | 5 | 18.182 | 2 | 8.448 |  | 0 | 12 | 44.172 | 1 | 4.224 | 1 | 4.224
WP2 months |  | 0 | 1 | 3.636 | 2 | 8.448 | 2 | 8.897 | 5 | 20.981 | 1 | 4.224 | 3 | 13.121
WP3 months |  | 0 | 3 | 10.909 | 5 | 21.12 | 4 | 17.794 | 12 | 49.823 | 2.5 | 10.56 | 6.5 | 28.354
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 3 | 10.909 | 3 | 12.672 | 1 | 4.4485 | 7 | 28.0295 | 1.5 | 6.336 | 2.5 | 10.7845
Zorba | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.97 | 4.97 | 5.2505 | 5.11 | 5.544 | 5.25 | 5.8482 | 5.39
WP1 months | 1 | 4.97 |  | 0 |  | 0 |  | 0 | 1 | 4.97 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 1 | 5.2505 | 2 | 11.088 | 1 | 5.8482 | 4 | 22.1867 | 1 | 5.544 | 2 | 11.3922
WP3 months |  | 0 |  | 0 | 2 | 11.088 | 3 | 17.5445 | 5 | 28.6324 | 1 | 5.544 | 4 | 23.0885
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Price | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6.93 | 6.93 | 7.3261 | 7.13 | 7.7405 | 7.33 | 8.17 | 7.53
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 1 | 7.3261 | 3 | 23.2214 | 2 | 16.3401 | 6 | 46.8876 | 1.5 | 11.6107 | 3.5 | 27.9508
WP3 months |  | 0 |  | 0 | 1 | 7.7405 | 1 | 8.17 | 2 | 15.9105 | 0.5 | 3.8702 | 1.5 | 12.0403
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Clark | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.58 | 4.58 | 4.8395 | 4.71 | 5.111 | 4.84 | 5.3816 | 4.96
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 1 | 5.111 | 2 | 10.7632 | 3 | 15.8742 | 0.5 | 2.5555 | 2.5 | 13.3187
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 6 | 22.512 | 5 | 18.182 | 2 | 8.448 | 0 | 0 | 13 | 49.142 | 1 | 4.224 | 1 | 4.224
WP2 | 0 | 0 | 3 | 16.2126 | 7 | 42.7574 | 5 | 31.0852 | 15 | 90.0553 | 3.5 | 21.3787 | 8.5 | 52.464
WP3 | 0 | 0 | 3 | 10.909 | 9 | 45.0595 | 10 | 54.2717 | 22 | 110.2402 | 4.5 | 22.5298 | 14.5 | 76.8015
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 3 | 10.909 | 3 | 12.672 | 1 | 4.4485 | 7 | 28.0295 | 1.5 | 6.336 | 2.5 | 10.7845
Sum | 6 | 22.512 | 14 | 56.2126 | 21 | 108.937 | 16 | 89.8054 | 57 | 277.467 | 10.5 | 54.4685 | 26.5 | 144.2739
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Manchester
Manchester
Hughes-Jones | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 5.94 | 5.94 | 6.5246 | 6.35 | 6.5683 | 6.22 | 6.9115 | 6.37
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 5.94 | 2 | 13.0493 | 2 | 13.1366 | 1 | 6.9115 | 6 | 39.0373 | 1 | 6.5683 | 2 | 13.4798
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kelly | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.5 | 3.5 | 4.1408 | 4.03 | 6.6528 | 6.3 | 6.9982 | 6.45
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 3.5 | 1 | 4.1408 | 1 | 6.6528 | 1 | 6.9982 | 4 | 21.2919 | 0.5 | 3.3264 | 1.5 | 10.3247
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thompson | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.52 | 5.52 | 6.5246 | 6.35 | 6.5683 | 6.22 | 6.9115 | 6.37
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 5.52 | 1 | 6.5246 | 4 | 26.2733 | 4 | 27.6458 | 10 | 65.9637 | 2 | 13.1366 | 6 | 40.7824
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Snow | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums
Monthly cost | 5.45 | 5.45 | 6.0931 | 5.93 | 6.7373 | 6.38 | 7.3238 | 6.75
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 5.45 | 1 | 6.0931 | 1 | 6.7373 | 1 | 7.3238 | 4 | 25.6041 | 0.5 | 3.3686 | 1.5 | 10.6924
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Freestone | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 3.74 | 3.74 | 4.3977 | 4.28 | 4.7942 | 4.54 | 5.2297 | 4.82
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 3.74 | 1 | 4.3977 | 2 | 9.5885 | 2 | 10.4594 | 6 | 28.1856 | 1 | 4.7942 | 3 | 15.2536
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elvin | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.8 | 2.8 | 3.6168 | 3.52 | 3.4954 | 3.31 | 3.7649 | 3.47
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 2.8 | 1 | 3.6168 | 2 | 6.9907 | 2 | 7.5299 | 6 | 20.9374 | 1 | 3.4954 | 3 | 11.0253
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perry | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 2.8 | 2.8 | 3.6168 | 3.52 | 2.8195 | 2.67 | 3.038 | 2.8
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months | 1 | 2.8 | 1 | 3.6168 | 1 | 2.8195 | 1 | 3.038 | 4 | 12.2743 | 0.5 | 1.4098 | 1.5 | 4.4478
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 2 | 9.44 | 3 | 17.1901 | 3 | 19.7894 | 2 | 13.9097 | 10 | 60.3292 | 1.5 | 9.8947 | 3.5 | 23.8044
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 5 | 20.31 | 5 | 24.249 | 10 | 52.4093 | 10 | 55.9969 | 30 | 152.9651 | 5 | 26.2046 | 15 | 82.2015
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 7 | 29.75 | 8 | 41.4391 | 13 | 72.1987 | 12 | 69.9065 | 40 | 213.2943 | 6.5 | 36.0994 | 18.5 | 106.0059
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RHUL
RHUL
Wu | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.5 | 3.5 | 3.699 | 3.6 | 3.8966 | 3.69 | 4.1121 | 3.79
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 3 | 4.837 | 6 | 23.3798 | 15 | 61.6823 | 24 | 89.8991 | 3 | 11.6899 | 18 | 73.3722
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 2 | 4.837 | 6 | 23.3798 | 6 | 24.6729 | 14 | 52.8897 | 3 | 11.6899 | 9 | 36.3628
Salvatore | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.8 | 4.8 | 5.1375 | 5 | 5.3011 | 5.02 | 5.6745 | 5.23
WP1 months | 1 | 4.7 | 1 | 5 |  | 0 |  | 0 | 2 | 9.7 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months | 1 | 4.7 | 1 | 5 | 6 | 31.8067 | 6 | 34.0473 | 14 | 75.554 | 3 | 15.9034 | 9 | 49.9507
Green | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.88 | 5.88 | 6.052 | 5.89 | 6.2304 | 5.9 | 6.4123 | 5.91
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 1 | 5.85 | 3 | 18.03 | 4 | 24.9216 | 2 | 12.8247 | 10 | 61.6263 | 2 | 12.4608 | 4 | 25.2855
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1 | 4.7 | 1 | 5 | 0 | 0 | 0 | 0 | 2 | 9.7 | 0 | 0 | 0 | 0
WP2 | 1 | 5.85 | 6 | 22.867 | 10 | 48.3014 | 17 | 74.507 | 34 | 151.5254 | 5 | 24.1507 | 22 | 98.6577
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 1 | 4.7 | 3 | 9.837 | 12 | 55.1866 | 12 | 58.7202 | 28 | 128.4438 | 6 | 27.5933 | 18 | 86.3135
Sum | 3 | 15.25 | 10 | 37.704 | 22 | 103.488 | 29 | 133.2271 | 64 | 289.6692 | 11 | 51.744 | 40 | 184.9711
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## UCL
UCL
Bartsch | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 3.54 | 3.54 | 3.7709 | 3.67 | 4.0445 | 3.83 | 4.2966 | 3.96
WP1 months | 0.5 | 2 | 0 | 0 |  | 0 |  | 0 | 0.5 | 2 | 0 | 0 | 0 | 0
WP2 months |  | 0 | 0 | 0 | 7 | 28.3114 | 5 | 21.483 | 12 | 49.7944 | 3.5 | 14.1557 | 8.5 | 35.6387
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 | 0 | 0 | 5 | 20.2224 | 3 | 12.8898 | 8 | 33.1122 | 2.5 | 10.1112 | 5.5 | 23.001
Warren | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.61 | 4.61 | 4.7881 | 4.66 | 5.2483 | 4.97 | 5.4576 | 5.03
WP1 months | 1 | 4.61 | 1 | 4.7881 |  | 0 |  | 0 | 2 | 9.3981 | 0 | 0 | 0 | 0
WP2 months | 2 | 9.22 | 5 | 23.9408 | 6 | 31.4899 | 3 | 16.3727 | 16 | 81.0233 | 3 | 15.745 | 6 | 32.1176
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Postranecky | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.13 | 5.13 | 5.2711 | 5.13 | 6.0192 | 5.7 | 6.1845 | 5.7
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months | 2 | 10.26 | 4 | 21.0843 | 6 | 36.1152 | 3 | 18.5535 | 15 | 86.013 | 3 | 18.0576 | 6 | 36.6111
WP3 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 1.5 | 6.61 | 1 | 4.7881 | 0 | 0 | 0 | 0 | 2.5 | 11.3981 | 0 | 0 | 0 | 0
WP2 | 4 | 19.48 | 9 | 45.0251 | 19 | 95.9165 | 11 | 56.4091 | 43 | 216.8307 | 9.5 | 47.9582 | 20.5 | 104.3674
WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 5 | 20.2224 | 3 | 12.8898 | 8 | 33.1122 | 2.5 | 10.1112 | 5.5 | 23.001
Sum | 5.5 | 26.09 | 10 | 49.8132 | 24 | 116.1389 | 14 | 69.299 | 53.5 | 261.341 | 12 | 58.0694 | 26 | 127.3684
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RAL PPD
RAL PPD
Tyndel | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 6.5 | 6.5 | 6.6787 | 6.5 | 6.864 | 6.5 | 7.0525 | 6.5
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 1 | 6.5 | 1 | 6.6787 | 1 | 6.864 | 1 | 7.0525 | 4 | 27.0953 | 0.5 | 3.432 | 1.5 | 10.4845
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Villani | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 6.5 | 6.5 | 6.6787 | 6.5 | 6.864 | 6.5 | 7.0525 | 6.5
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 5 | 32.5 | 5 | 33.3937 | 5 | 34.32 | 5 | 35.2625 | 20 | 135.4762 | 2.5 | 17.16 | 7.5 | 52.4225
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stanitski | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 4.92 | 4.92 | 5.0553 | 4.92 | 5.1955 | 4.92 | 5.3382 | 4.92
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months |  | 0 |  | 0 | 12 | 62.3462 | 12 | 64.0584 | 24 | 126.4046 | 6 | 31.1731 | 18 | 95.2315
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 6 | 39 | 6 | 40.0725 | 18 | 103.5302 | 18 | 106.3734 | 48 | 288.9761 | 9 | 51.7651 | 27 | 158.1385
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 6 | 39 | 6 | 40.0725 | 18 | 103.5302 | 18 | 106.3734 | 48 | 288.9761 | 9 | 51.7651 | 27 | 158.1385
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## RAL ID
RAL ID
Turchetta | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Sums |  | To end Sept 2007 |  | Rest of project
Monthly cost | 10.89 | 10.89 | 11.508 | 11.2 | 12.144 | 11.5 | 12.8247 | 11.82
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 1 | 10.89 | 1 | 11.508 | 1 | 12.144 | 1 | 12.8247 | 4 | 47.3667 | 0.5 | 6.072 | 1.5 | 18.8967
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crooks | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9
Monthly cost | 5.69 | 5.69 | 6.0828 | 5.92 | 6.4838 | 6.14 | 6.9006 | 6.36
WP1 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 months | 3 | 17.07 | 12 | 72.9936 | 12 | 77.8061 | 9 | 62.1054 | 36 | 229.9751 | 6 | 38.903 | 15 | 101.0084
WP4 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 months |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total costs
WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP3 | 4 | 27.96 | 13 | 84.5016 | 13 | 89.9501 | 10 | 74.9301 | 40 | 277.3418 | 6.5 | 44.975 | 16.5 | 119.9051
WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sum | 4 | 27.96 | 13 | 84.5016 | 13 | 89.9501 | 10 | 74.9301 | 40 | 277.3418 | 6.5 | 44.975 | 16.5 | 119.9051
Indexation | 1 |  | 1.0275 |  | 1.056 |  | 1.085

## Other
|  | 2005/6 |  | 2006/7 |  | 2007/8 |  | 2008/9 |  | Total |  | Left | Left for
|  | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Allocated | Actual | in budget | 2008/9
Equipment | WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| WP2 | 11 | 0 | 36.99 | 8.114 | 65 | 24 | 16.28 |  | 118.1 | 32.114 | 85.986 | 44.986
| WP3 | 0 | 0 | 3.08 | 15.107 | 63 | 34.8 | 108.5 |  | 206.6 | 49.907 | 156.693 | 128.493
| WP4 | 0 | 0 | 0 | 0 | 2.11 | 0 | 17.36 |  | 19.5 | 0 | 19.5 | 17.39
| WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total | 11 | 0 | 40.07 | 23.221 | 130.11 | 58.8 | 142.14 | 0 | 344.2 | 82.021 | 262.179 | 190.869
Consumables | WP1 | 6 | 0.407 | 5.14 | 3.875 | 0 | 2.2 | 0 |  | 11.1 | 6.482 | 4.618 | 6.818
| WP2 | 4 | 0 | 9.25 | 13.908 | 6.34 | 1.69 | 0 |  | 19.6 | 15.598 | 4.002 | -0.648
| WP3 | 2 | 1.228 | 1.03 | 0.017 | 9.5 | 5 | 46.66 |  | 59.2 | 6.245 | 52.955 | 48.455
| WP4 | 0 | 0 | 3.08 | 0 | 2.11 | 0 | 4.34 |  | 9.5 | 0 | 9.5 | 7.39
| WP5 | 2 | 0 | 0 | 0 | 2.11 | 0 | 0 |  | 4.1 | 0 | 4.1 | 1.99
| Total | 14 | 1.635 | 18.5 | 17.8 | 20.06 | 8.89 | 51 | 0 | 103.5 | 28.325 | 75.175 | 64.005
Travel | WP1 | 34 | 16.7384 | 55.49 | 34.0718 | 32.2 | 20.9 | 0 |  | 111.7 | 71.7102 | 39.9898 | 28.6898
| WP2 | 6 | 2.9538 | 6.17 | 3.7885 | 9.5 | 6.17 | 3.26 |  | 24.9 | 12.9123 | 11.9877 | 8.6577
| WP3 | 1 | 0.49231 | 5.14 | 3.156 | 7.39 | 4.9 | 17.36 |  | 30.9 | 8.5484 | 22.3516 | 19.8616
| WP4 | 1 | 0.49231 | 1.03 | 0.63244 | 1.06 | 0.6 | 1.09 |  | 4.2 | 1.7247 | 2.4753 | 2.0153
| WP5 | 7 | 3.4461 | 13.36 | 8.2033 | 27.7 | 18 | 10.85 |  | 50.2 | 29.6494 | 20.5506 | 10.8506
| Total | 49 | 24.123 | 81.19 | 49.852 | 77.85 | 50.57 | 32.56 | 0 | 221.9 | 124.545 | 97.355 | 70.075
Travel
| General |  | 9.741 |  | 5.98
| Birmingham |  | 1.462 |  | 8.007
| Cambridge |  | 1.546 |  | 11.235
| Imperial |  | 2.346 |  | 9.555
| Manchester |  | 3.404 |  | 2.585
| RAL-TD |  | 0 |  | 0
| RAL-PPD |  | 0 |  | 0.564
| RHUL |  | 1.878 |  | 8.497
| UCL |  | 3.746 |  | 3.429
| Total | 49 | 24.123 | 81.19 | 49.852