Milestone Tables

| Table 1. Milestones for the period Jan 2008 – Jul 2008 |
| --- |
| WP1.24 Submit paper on electron results | Mar 2008 | Complete May 2008 |
| WP1.29 Complete internal report on hadron data | Mar 2008 | Complete May 2008 |
| WP2.16 Test panel 1 complete | Jan 2008 | Complete Apr 2008 |
| WP2.45 Demonstrate optically switched network | Jan 2008 | Achieved |
| WP2.83 Initial system complete | Jan 2008 | Achieved |
| WP2.51 LDA-DIF link operational at electrical level | Mar 2008 | Achieved |
| WP2.20 DIF completed | May 2008 | Aug 2008 |
| WP2.64 Demonstrate trigger and C + C interface | Jun 2008 | Sep 2008 |
| WP3.15 Second sensor preliminary design review | Jan 2008 | Complete May 2008 |
| WP3.16 Second sensor interim design review | Apr 2008 | Deleted |
| WP3.17 Second sensor design review | Jun 2008 | Achieved |
| WP3.18 Second sensor design to foundry | Jul 2008 | Achieved |
| WP4.6 End of module – 3D design complete | Apr 2008 | Deleted |
| WP4.11 Module assembly – initial wafers expected | Apr 2008 | Achieved |
| WP5.28 Simulation of MAPS test beam | Mar 2008 | ??? |
| WP5.38 Report on hadronic modelling studies with test beam | Jun 2008 | ??? |

| Table 2. Milestones for the period Aug 2008 – Dec 2008 |
| --- |
| WP1.33 Successful completion of FNAL test beam run | Dec 2008 |
| WP2.69 Demonstrate work-ability from single trigger | Oct 2008 |
| WP2.53 Working LDA with C&C and ODR | Dec 2008 |
| WP2.92 Complete basic DAQ and run control | Dec 2008 |
| WP3.20 Second fabrication complete | Oct 2008 |

| Table 3 – Overall milestone list as updated July 2008 |
| --- |
|  | As at Dec 2007 | As at July 2008 Changes in bold | Delay due to | Affects critical path? | See note |
|  |  |  | UK? | Other Collabor-ators? |  |  |
| WP1.9 Successful end of DESY test beam run | May 2005 | Achieved |  |  |  |  |
| WP1.19 Successful end of 2006 CERN test beam run | Oct 2006 | Achieved |  |  |  |  |
| WP1.27 Present interim results at LCWS07 | May 2007 | Achieved |  |  |  |  |
| WP1.14 Complete analysis of DESY data | Jun 2007 | Complete Oct 2007 |  |  |  |  |
| WP1.20 Successful end of 2007 CERN test beam run | Jul 2007 | Complete Aug 2007 | N |  | N |  |
| WP1.24 Submit paper on electron results | Mar 2008 | Complete May 2008 | Y | Y |  |  |
| WP1.29 Complete internal report on hadron data | Mar 2008 | Complete May 2008 | Y | Y |  |  |
| WP1.33 Successful completion of FNAL test beam run | Dec 2008 | Dec 2008 | N | Y |  |  |
| WP1.37 Submit paper on hadron results | Sep 2009 | Sep 2009 |  |  |  |  |
| WP2.75 Buy PCI cards | May 2006 | Achieved |  |  |  |  |
| WP2.27 FPGA 1Gb Ethernet MAC firmware complete | Jul 2006 | Achieved |  |  |  |  |
| WP2.57 Present simulation results | Dec 2006 | Complete Apr 2007 |  |  |  |  |
| WP2.9 Test bench 0 hardware ready and commissioned | Jan 2007 | Complete May 2007 |  |  |  |  |
| WP2.30 Report on FPGA Ethernet work | Jan 2007 | Complete Apr 2007 |  |  |  |  |
| WP2.41 Acquire optical switch | Mar 2007 | Complete May 2007 | Y | N | N |  |
| WP2.79 Initial prototype complete | Mar 2007 | Achieved |  |  |  |  |
| WP2.60 Make proposal for robust/flexible system | Jun 2007 | Achieved |  |  |  |  |
| WP2.72 Demonstrate remote FPGA reset and reconfigure | Jun 2007 | Deleted |  |  |  |  |
| WP2.12 Concepts established for 1.5m data path | Jul 2007 | Achieved |  |  |  |  |
| WP2.89 DAQ software choice | Oct 2007 | Achieved |  |  |  |  |
| WP2.14 Test bench 1 hardware ready and complete | Nov 2007 | Achieved |  |  |  |  |
| WP2.16 Test panel 1 complete | Jan 2008 | Complete Apr 2008 |  |  |  |  |
| WP2.45 Demonstrate optically switched network | Jan 2008 | Achieved |  |  |  |  |
| WP2.83 Initial system complete | Jan 2008 | Achieved |  |  |  |  |
| WP2.51 LDA-DIF link operational at electrical level | Mar 2008 | Achieved |  |  |  |  |
| WP2.20 DIF completed | May 2008 | Aug 2008 |  |  |  |  |
| WP2.64 Demonstrate trigger and C + C interface | Jun 2008 | Sep 2008 |  |  |  |  |
| WP2.38 Report on 10Gb performance | Aug 2008 | Deleted |  |  |  |  |
| WP2.69 Demonstrate work-ability from single trigger | Oct 2008 | Oct 2008 |  |  |  |  |
| WP2.53 Working LDA with C&C and ODR | Dec 2008 | Dec 2008 |  |  |  |  |
| WP2.92 Complete basic DAQ and run control | Dec 2008 | Dec 2008 |  |  |  |  |
| WP2.23 ECAL DIF available for test beams | Mar 2009 | Mar 2009 |  |  |  |  |
| WP2.49 Delivery of busy system | Mar 2009 | Mar 2009 |  |  |  |  |
| WP2.72 Demonstrate remote FPGA reset and reconfigure | Mar 2009 | Mar 2009 |  |  |  |  |
| WP3.3 Preliminary design review | Apr 2006 | Achieved |  |  |  |  |
| WP3.5 First sensor interim design review | Oct 2006 | Complete Jan 2007 |  |  |  |  |
| WP3.6 First sensor design review | Dec 2006 | Complete Mar 2007 | Y | N | Y | 1 |
| WP3.7 First sensor design to foundry | Jan 2007 | Complete Apr 2007 | Y | N | Y | 1 |
| WP3.9 First sensor fabrication complete | May 2007 | Complete Jul 2007 | Y | N | Y | 1 |
| WP3.15 Second sensor preliminary design review | Jan 2008 | Complete May 2008 |  |  |  |  |
| WP3.16 Second sensor interim design review | Apr 2008 | Deleted | Y | N | Y | 1 |
| WP3.17 Second sensor design review | Jun 2008 | Achieved | Y | N | Y | 1 |
| WP3.18 Second sensor design to foundry | Jul 2008 | Achieved | Y | N | Y | 1 |
| WP3.20 Second fabrication complete | Oct 2008 | Sep 2008 | Y | N | Y | 1 |
| WP3.25 Second sensor beam tests start | Jun 2009 | Deleted | Y | N | Y | 1 |
| WP4.6 End of module – 3D design complete | Apr 2008 | Deleted |  |  |  |  |
| WP4.11 Module assembly – initial wafers expected | Apr 2008 | Achieved |  |  |  |  |
| WP5.14 Present initial result from single particle studies | Mar 2006 | Achieved |  |  |  |  |
| WP5.26 MAPS implemented in Mokka | May 2006 | Achieved |  |  |  |  |
| WP5.33 Status report at regional workshop | May 2006 | Achieved |  |  |  |  |
| WP5.4 Comparison of existing PFAs | Jun 2006 | Achieved |  |  |  |  |
| WP5.8 Release of V1 of algorithm | Aug 2006 | Achieved |  |  |  |  |
| WP5.34 Generic physics analysis implemented | Sep 2006 | Achieved |  |  |  |  |
| WP5.16 Present first physics benchmarks results at Valencia | Nov 2006 | Deleted | Y | N | N | 2 |
| WP5.11 Presentation of physics benchmark results at LCWS07 | Apr 2007 | May 2007 | N |  | N | 3 |
| WP5.36 Alternative benchmark analysis available | Sep 2007 | Sep 2007 |  |  |  |  |
| WP5.24 First results from mechanical imperfections simulation | Dec 2007 | Dec 2007 |  |  |  |  |
| WP5.28 Simulation of MAPS test beam | Mar 2008 | Mar 2008 |  |  |  |  |
| WP5.38 Report on hadronic modelling studies with test beam | Jun 2008 | Jun 2008 |  |  |  |  |

Notes:

1. Simulation studies showed that additional design work of a deep p-well process by the foundry was required to achieve the target signal:noise ratio.

2. Initial results were presented earlier to collaboration meetings and we decided to wait until LCWS07 before presenting further results.

3. LCWS07 date fixed as May 2007 after we had set this benchmark.

4. Phase 1 of ASIC development skipped by our collaborators.