## Slide 1: UK CMS Upgrade Oversight Committee
University of Bristol
Brunel University London
Imperial College London
Rutherford Appleton Laboratory
27 May 2015

## Slide 2: Overview
Snapshots of LHC & CMS status
  CMS and LHC are well into recommissioning phase
Summary of UK upgrade project
  Recent WP progress
Finances

## Slide 3: 2015 LHC schedule
as of 4 May
Generally good progress
  few week slippage compared to Nov 2014
  physics foreseen from 1 June
  but..

## Slide 4
CMS WGM 4 May
CERN Bulletin 22 May: no beam losses at obstacle in latest intensity tests

## Slide 5
CMS WGM 4 May

## Slide 6
CMS WGM 4 May

## Slide 7
CMS WGM 4 May

## Slide 8: Forward calorimeter decision
High Granularity option chosen mainly for risk reasons
    employs similar technology to Tracker (silicon, CO2, ASICs)
  T. Virdee interim PM
  possible UK role under consideration
    significant supplementary funding via ERC, plus PRD post

## Slide 9: UK R&D status

## Slide 10: Last 6 months
WP2:
  continued steady progress with CBC3 design
    expected CBC3 submission Feb 2016 in MOSIS run
  First series of FC7 production complete but unexpected problems
WP3: progress towards installation of TDR trigger
  UK Stage-1 commitments essentially complete
  UK Layer-2 for 2016 trigiger in place and being commissioned
    details to follow
WP2 & WP3: progress on TMTT studies
CMS TP delayed to LHCC to June 2015
    decision on forward calorimetry made April 2015, endorsed CB 8 May

## Slide 11: Overview of CBC activities
CBC2 characterization complete (reported last time)
  including ionizing irradiation (to 180 Mrads!) and SEU testing
  results informing CBC3 design
CBC2 based module tests continue
  mini-module with irradiated sensors in test beam in June
  full-size module test beam in November
CBC3 design now in full flow
  all modifications and additional features agreed with CMS systems team collaborators
  specification document complete and circulated

## Slide 12
CBC3 status
Pipeline
Control
Front End
Amplifiers
vth
vth
vth
vth
512 Deep
Pipeline (12.8µs)
+
32 Deep
Buffer
Test
Pulse
Generator
Bias
Generator
Slow Control
Offset Correction & Correlation
1
254
I2C
Channel Mask
SLVS
Input
Data Packet
Assembly &
Transmission
Stub &
L1 Data
VDDD
1.2V+/-10%
Band-gap
LDO
VDDA
1.0 V
Cluster Width Discrimination
Hit Detect
PISO Shift Register
Comparators
Stub Gathering Logic
Fast Control
 254 Channels 
320 MHz
SLVS
Clock
40 MHz
Differential
Clock
DLL
DLL
40 MHz Region
320 MHz
Region
Nearest
Neighbour
Signals
I2C Registers
Bend lookup formatting
Complete
In progress
To do
design work progressing
main new features are:
stub address generation & transmission off-chip @ 320 Mbps
longer L1 pipeline (12.8 usec)
higher L1 trigger rate capability (up to 1 MHz)
major new blocks are:
stub gathering logic
  complete
data packet assembly & transmission
  at advanced stage
review meetings held at key stages to monitor progress
Preliminary Layout
Nearest
Neighbour
Signals

## Slide 13: CBC3 plan
ready for
production
2014
2015
2016
2017
2018
CBC3 design & production
CBC3 in hand
CBC4 design & test
engineering run
CBC3 test (& modules based on CBC3)
modules based on CBC2
concentrator prototype in FPGA
modules based on CBC3 and concentrator ASIC
(need to integrate DC-DC and link components)
plan to submit CBC3 through MOSIS in February
  limited number of chips but ~ half the cost of full wafer run
  can expect chips in hand ~ May
    (small schedule slippage but have to comply with fixed submission dates)

## Slide 14: FC7
Problems discovered in boards built for TCDS project
  upgraded CMS TTC system, on tight schedule

## Slide 16
with help from Xilinx failure analysis

## Slide 17: FC7 current status
Problem is now believed to be understood but proceeding with caution
  simple repair to existing boards
    however stressed boards likely to have been damaged
  error corrected in layout for R2
  design modified to be conservative in all respects
  internal design review with CERN, and some outside experts, April
  replacements underway
    existing design, with correction for urgent
    needs (TCDS and pixel prototyping) reordered
    R2 ready for submission very soon
Some important lessons everywhere
  listed in report

## Slide 18: WP3 objectives and status
Calorimeter trigger status
  to be updated orally at meeting
    review held April – report not yet issued
    commissioning status (Stage-1 & TDR)
    Plan B readiness
  all MP7s required for UK commitments delivered
    but some manufacturing issues and PCB material is under consideration for the future, as with the FC7

## Slide 19: 2016 Calorimeter Trigger Milestones
Milestones related to CTP7
  25.10.2014 3 CTP7s at CERN
  15.11.2014 4 CTP7s at CERN (includes the previous)
  20.01.2015 8 CTP7s at CERN (includes the previous)
  28.01.2015 12 CTP7s at CERN (includes the previous)
  25.03.2015 28 CTP7s at CERN (includes the previous)
  08.04.2015 36 CTP7s at CERN (includes the previous)
Milestones related to commissioning of the trigger
  22.12.2014 Layer-2 – Patch Panel – Layer-1 Commissioned
  16.01.2015 oSLB and HF uHTR systems commissioned
  19.01.2015 Layer-2 – Patch Panel – Layer-1 Connected to uGT
  25.11.2014 First Version of CTP7 firmware (incl. input playback)
  09.03.2015 Final Version of CTP7 firmware (except DAQ link)
  17.02.2015 Final design of Algorithms and data format defined
    Decision to upgrade 2016 trigger inputs from ECAL and HCAL
  17.06.2015 B/E uHTR system connected to the trigger - Commissioned
  02.09.2015 System ready for parallel data taking

## Slide 20: MP7 order status
Following prototyping/pre-production, two orders of 16 boards
  Prod-1: 16 delivered (Hapro) + 16 from Exception, essentially complete
    a bit of a struggle with UK company
  Hapro orders of 8 + 32 launched in 2014 (Prod-2 and Supp Prod-1)
    assembly error with first 8, so delay
      now complete
    manufacturing error with pre-series cards of 32 order.
      delay while new PCBs procured, delivery in August

## Slide 21: MP-Ultra: Successor to the MP7
8Gb of RLDRAM3 in four independent banks
PCIe form-factor – easier to manufacture than µTCA
Two variants planned spanning 3-generations/families of FPGA:
  48-link variant – very low-cost with maximal logic/bandwidth ratio
  96-link variant (Ultrascale FPGA) – maximum bandwidth
  96-link variant (Ultrascale+ FPGA) – maximum bandwidth & logic
Top
Bottom
Successor to the MP7 based on Xilinx Ultrascale and Ultrascale+ FPGAs
Up to 96+96 (Tx+Rx) links at up to 16Gbps: bandwidth > 1.5+1.5 Tbps

## Slide 22: Track-trigger progress
Now quite substantial UK-wide activity focusing on
  simulations
  algorithms for track finding in FPGA
  firmware design
  implementation in MP7 demonstrator system
Target: working demonstrator by August
  of course with limited objectives compared to final system

## Slide 23: Layout of fully Time-Multiplexed Track-Trigger
Focusing on demonstration of the concept
  entire tracker could be read out by MP7-like processing cards
  requires ~200 cards, segmented into 5 h regions
feed time-multiplexed data to regional processors
TM period of 24-36 BX possible using MP7s
module sharing
≤ 2 regions
simpler architecture
no deghosting
sharing defined by large luminous region in z

## Slide 24: Track-finding in FPGA
valid track where lines intersect
i.e. stubs which share the same (m,c)
Hardware requirements already feasible, but processing in FPGA very challenging
  exploring Hough transform approach:
  line in real space -> point in inverse space
pipelined dataflow
  natural with TM
  matches FPGA needs
find stubs in 2D
  2D histogram
selection to reduce number of candidates

## Slide 25: Status of demonstrator
Hardware exists in working form (from calo trigger)
  adapt for track-trigger time slice
  software validation under way
Firmware implementation of Hough array ready
  self-filling systolic array
  integrating with infrastructure firmware

## Slide 26: Finances
Expenditure – no special issues
  Staff expenditure essentially as foreseen
    including slight ramp-up in RAL TD, matching our delivery plan
  Travel also as foreseen – further LTA commitments under way
Materials & equipment
  WP2:
    CBC3 manufacture early 2016
  WP3:
    For purchases via CERN (FC7 & MP7) direct invoicing to Imperial now working well

## Slide 27: Conclusions
Milestones
  reported in document
Risks
  register revised
  no new risks, but MP7 and FC7 issues have materialised
Trigger project in crucial commissioning phase
  SP team has been playing significant role

## Slide 28: Further information