## Sheet1
FV/10.11.14 | 2011/1 | 2011/2 | 2012/1 | 2012/2 | 2013/1 | 2013/2 | 2014/1 | 2014/2 | 2015/1 | 2015/2 | 2016/1 | 2016/2 | 2017/1 | 2017/2 | 2018/1 | 2018/2
0. Tracker upgrade simplified plan
0.1. R&D
0.2. Design and fabrication of prototypes
0.3. Prototype test and qualification
0.4. System test
0.5. Final design / preproduction
0.6. Qualification
0.6. Final system test
0.7. Module construction
1. Electronic system for front-end module
1.1. Architecture
1.1.1 Break down front-end into functional blocks, define interfaces
1.1.2 Break down backend (readout, trigger and control paths)
1.2. Integration
1.2.1 Develop framework for module electronics integration and testing
1.2.2 Chain integration
1.2.2.1 Assemble chain 2xCBC2-GLIB-DAQ
1.2.2.2 Assemble chain 8xCBC2-GLIB-DAQ
1.2.2.3 Assemble chain 8xCBC3-DTC-DAQ
1.2.3 Lab system test and Beam tests with modules
1.3. Documentation
2. 2S-Pt Module electronics
2.1. Module Concept and Architecture
2.1.1 Define functional and mechanical requirements to electronics
2.1.2 3D modelling of module and services
2.1.3 Iterate based on prototype experience
2.2. Front-End chip
2.2.1 CBC testing, irradiation
2.2.2 Documentation
2.2.3 CBC2 design iteration
2.2.3.1. Freeze requirements
2.2.3.2. Fix design-bugs
2.2.3.3. Scale to 2x128 channels
2.2.3.4. Add Pt capability
2.2.3.5. C4 pad layout
2.2.3.6. Check compatibility with hybrid, C&C and system
2.2.3.7. Design and review
2.2.4 CBC2 production
2.2.5 CBC2 Testing (chip level)
2.2.6 CBC2 Testing (on 2xCBC2 hybrid)
2.2.6.1. Define and prepare test bench and vectors
2.2.6.2. Test functionality
2.2.7 CBC3 Design iteration/production
2.2.8 CBC3 Qualification
2.2.9 CBC4 Design iteration
2.2.10 CBC4 Engineering run
2.3. Concentrator
2.3.1 Specify
2.3.1.1. Establish requirements
2.3.1.2. Evaluate architectures and perform high level simulations
2.3.1.3. Check compatibility with hybrid, CBC and system
2.3.1.4. Design and review
2.3.2 Synthesis V1 in FPGA (L1 mux)
2.3.3 Synthesis V2 in FPGA (block synchronous)
2.3.4 Synthesis V3 in FPGA (full functionality)
2.3.5 FPGA-based Test System
2.3.5.1. Define and prepare test bench and vectors
2.3.5.2. Test functionality
2.3.6 Documentation, data formats
2.3.7 CIC1 Design and production
2.3.8 CIC1 Testing
2.4. Front End Hybrid
2.4.1 Market survey (informal)
2.4.1.1. Survey available technologies and materials
2.4.1.2. Procure and evaluate samples
2.4.2 Design 2xCBC2 and 8xCBC2 prototypes
2.4.2.1. Establish requirements
2.4.2.2. Evaluate alternative designs/fabrication sources
2.4.2.3. Check compatibility with CBC and system
2.4.2.4. Evaluate testability
2.4.2.5. Design and review
2.4.3 Define procurement framework
2.4.4 Market survey (formal)
2.4.5 Invitation to Tender for hybrid development
2.4.6 Production 2xCBC2 prototype
2.4.7 Testing 2xCBC2 prototype
2.4.6.1. Define and prepare test bench and vectors
2.4.6.2. Test Functionality
2.4.6.3. Test Environmental resistance
2.4.8 Production 8xCBC2 prototype
2.4.9 Test of 8xCBC2 prototype
2.4.10 Documentation
2.4.11 Impedance Controlled lines
2.4.12 Design iterations with selected companies
2.5. Front End Hybrid Test Setup
2.5.1 2xCBC2 Hybrid adaptor card (FMC)
2.5.2 8xCBC2 Hybrid adaptor card (FMC)
2.5.3 Hybrid test hardware, firmware and software
3. PS-Pt Module
3.1. Module concept and architecture
3.2. MPA chip
3.2.1 Requirements
3.2.2 Architecture
3.2.3 Design
3.2.4 Production
3.2.5 Test
3.2.6 Documentation
3.2.7 Design iteration MPA1
3.2.8 Production MPA1
3.2.9 MPA1 test
3.3. SSA chip
3.3.1 Requirements
3.3.2 Design SSA-Light
3.3.3 Production SSA-Light prototype
3.3.4Test
3.3.5Documentation
3.3.2 Design iteration SSA1
3.3.3 Production SSA1
3.3.9 SSA1 test
3.4. MaPSA
3.4.1 Design MaPSA-Light prototype
3.4.1.1. Establish requirements
3.4.1.2. Evaluate alternative designs/fabrication sources
3.4.1.3. Check compatibility with MPA and system
3.4.1.4. Evaluate testability
3.4.1.5. Design and review
3.4.2 Define procurement framework
3.4.3 Market survey (formal)
3.4.4 Production MaPSA-Light prototype
3.4.5 Iteration (second source etc)
3.4.6 Testing MaPSA-Light prototype
3.4.5.1. Define and prepare test bench and vectors
3.4.5.2. Test Functionality
3.4.5.3. Test Environmental resistance
3.4.7 Documentation
3.4.8 Full MaPSA mockup
3.4.8 Design iteration for full MaPSA prototype
3.4.9 Production of full prototype MaPSA1
3.4.10 Test of full prototype
4. Link
4.1. Low power GBT chip
4.1.1 Design
4.1.1.1. Establish requirements
4.1.1.2. Evaluate architectures and technologies
4.1.1.3. Evaluate packaging
4.1.1.4. Check compatibility with hybrid and system
4.1.1.5. Design and review
4.1.2 Production
4.1.3 Packaging
4.1.4 Testing (chip level)
4.1.2.1. Define and prepare test bench and vectors
4.1.2.2. Test functionality
4.1.5 Documentation
4.1.6 Design iteration
4.2. Low power GBLD chip
4.2.1 Establish requirements and options
4.2.2 Design
4.2.3 Production
4.2.4 Test
4.3. GBTIA chip
4.3.1 Iterate Design (V2)
4.3.2 Iterate Design (V3)
4.3.3 Production
4.3.4 Test
4.4. Small footprint low power VTRx
4.4.1 Feasibility study (small footprint)
4.4.1.1. Study concept and options (mechanical and electrical interfaces)
4.4.1.2. Fabricate prototype based on VL components + connector clip
4.4.1.3. Evaluate performance and conclude on feasibility
4.4.2 Rolling market survey of small footprint packages
4.4.3 Prototype low power small footprint LP-SF-VTRx
4.5. Optical Cabling
4.5.1 Check versatility of multi-ribbon cable
4.6. Backend opto
4.6.1 Survey MTx and MRx
5. Power
5.1. Powering architecture and system design
5.2. DC-DC converter
5.3. Service hybrid
5.4. LVPS
5.5. HVPS
5.6. Electrical cables
6. FED/C
6.1. GLIB-based prototype backend
6.2. FED-FEC design
8xCBC2
hybrid
Tested MaPSA-Light
SF-VL Feasibility
Low Power GBT Feasibility
CBC2 chip
MPA-light chip
VTRx+ demonstrator
Tested Full MaPSA1
GBLD V4.1
Low Power GBLD V5
TDR
TP
Concentrator V2 in FPGA
CBC3 chip
CBC4 chip
CIC1
2xCBC2 chain
8xCBC2 chain
GBLD feasibility V4
GBTIA feasibility V1
2xCBC2 hybrid
2xCBC2
8xCBC2
Concentrator V3 in FPGA
Hybrid Test System
GBTIA V2.1
GBTIA V2
M-Ribbon cable
versatility
8xCBC3 chain
8xCBC3
Tested CIC1
8xCBC2 2nd source
CBC3 + concentrator hybrid
GLIB-based FED/FEC
Tested CBC2
Tested MPA-light
Tested GBLD V4.1
Tested GBTIA V2.1
MaPSA-Light
MPA1
Concentrator data formats
Concentrator Spec
8xCBC2 stress
test
Diff lines choice
SSA-light chip
Tested SSA-light
SSA1
Tested SSA1
Tested MPA1