## Sheet1
FV/11.10.16 | 2011/1 | 2011/2 | 2012/1 | 2012/2 | 2013/1 | 2013/2 | 2014/1 | 2014/2 | 2015/1 | 2015/2 | 2016/1 | 2016/2 | 2017/1 | 2017/2 | 2018/1 | 2018/2 | 2019/1 | 2019/2 | 2020/1 | 2020/2 | 2021/1 | 2021/2 | 2022/1 | 2022/2 | 2023/1 | 2023/2 | 2024/1 | 2024/2 | 2025/1 | 2025/2 | 2026/1 | 2026/2
0. Tracker upgrade simplified plan
0.1. R&D
0.2. Design and prototyping
0.3. Engineering and preproduction
0.4. Production and assembly
0.5. Pre-installation and testing, installation, commissionning
0.5.1 Preparation in UXC
0.5.2 Installation and commissioning
[6 empty] | LS1 | [12 empty] | LS2 | [8 empty] | LS3
1. Electronic system for front-end module
1.1. Architecture
1.1.1 Break down front-end into functional blocks, define interfaces
1.1.2 Break down backend (readout, trigger and control paths)
1.2. Integration
1.2.1 Develop framework for module electronics integration and testing
1.2.2 Chain integration
1.2.2.1 Assemble chain 2xCBC2-GLIB-DAQ
1.2.2.2 Assemble chain 8xCBC2-GLIB-DAQ
1.2.2.3 Assemble chain 8xCBC3-DTC-DAQ
1.2.3 Lab system test and Beam tests with modules
1.3. Documentation
2. 2S-Pt Module electronics
2.1. Module Concept and Architecture
2.1.1 Define functional and mechanical requirements to electronics
2.1.2 3D modelling of module and services
2.1.3 Iterate based on prototype experience
2.2. Front-End chip
2.2.1 CBC testing, irradiation
2.2.2 Documentation
2.2.3 CBC2 design iteration
2.2.3.1. Freeze requirements
2.2.3.2. Fix design-bugs
2.2.3.3. Scale to 2x128 channels
2.2.3.4. Add Pt capability
2.2.3.5. C4 pad layout
2.2.3.6. Check compatibility with hybrid, C&C and system
2.2.3.7. Design and review
2.2.4 CBC2 production
2.2.5 CBC2 Testing (chip level)
2.2.6 CBC2 Testing (on 2xCBC2 hybrid)
2.2.6.1. Define and prepare test bench and vectors
2.2.6.2. Test functionality
2.2.7 CBC3 Design iteration/production
2.2.8 CBC3 Testing and Qualification
2.2.9 CBC4 Design iteration
2.2.10 CBC4 Engineering run
2.3. Concentrator
2.3.1 Specify
2.3.1.1. Establish requirements
2.3.1.2. Evaluate architectures and perform high level simulations
2.3.1.3. Check compatibility with hybrid, CBC and system
2.3.1.4. Design and review
2.3.2 Synthesis V1 in FPGA (L1 mux)
2.3.3 Synthesis V2 in FPGA (block synchronous)
2.3.4 Synthesis V3 in FPGA (full functionality)
2.3.5 FPGA-based Test System
2.3.5.1. Define and prepare test bench and vectors
2.3.5.2. Test functionality
2.3.6 Documentation, data formats
2.3.7 CIC1 Design and production
2.3.8 CIC1 Testing
2.3.9 CIC iteration
2.4. Front End Hybrid
2.4.1 Market survey (informal)
2.4.1.1. Survey available technologies and materials
2.4.1.2. Procure and evaluate samples
2.4.2 Design 2xCBC2 and 8xCBC2 prototypes
2.4.2.1. Establish requirements
2.4.2.2. Evaluate alternative designs/fabrication sources
2.4.2.3. Check compatibility with CBC and system
2.4.2.4. Evaluate testability
2.4.2.5. Design and review
2.4.3 Define procurement framework
2.4.4 Market survey (formal)
2.4.5 Invitation to Tender for hybrid development
2.4.6 Production 2xCBC2 prototype
2.4.7 Testing 2xCBC2 prototype
2.4.6.1. Define and prepare test bench and vectors
2.4.6.2. Test Functionality
2.4.6.3. Test Environmental resistance
2.4.8 Production 8xCBC2 prototype
2.4.9 Test of 8xCBC2 prototype
2.4.10 Documentation
2.4.11 Impedance Controlled lines
2.4.12 FEH iterations with selected companies
2.5. Front End Hybrid Test Setup
2.5.1 2xCBC2 Hybrid adaptor card (FMC)
2.5.2 8xCBC2 Hybrid adaptor card (FMC)
2.5.3 CBC2 Hybrid test hardware, firmware and software
2.5.4 Iterate FEH test setup
2.6. Service Hybrid
2.6.1 Design SEH demonstrator
2.6.2 Production SEH demonstrator
2.6.3 Test SEH demonstrator
2.6.4 Design SEH prototype (incl GBTx, DC/DC, VTRx+)
2.6.5 Production SEH prototype | [24 empty] | Here is my tentative roadmap for wafer bumping thinning and dicing.
2.6.6 Test SEH prototype
2.6.7 Service Hybrid iterations | [24 empty] | - CBC3, 10 wafers (8”), March 2017
3. PS-Pt Module | [24 empty] | - MPA1, 10 wafers (12”), Sept 2017
3.1. Module concept and architecture | [24 empty] | - CBC4, 10 wafers (8”), Sept 2018
3.2. MPA chip | [24 empty] | - MPA2, 10 wafers (12”), Sept 2018 (includes also CIC2)
3.2.1 Requirements | [24 empty] | - CBC4, 300 wafers (8”), Sept 2019
3.2.2 Architecture | [24 empty] | - MPA2, 500 wafers (12”), Sept 2019 (includes also CIC2)
3.2.3 Design
3.2.4 Production
3.2.5 Test
3.2.6 Documentation
3.2.7 Design iteration MPA1
3.2.8 Production MPA1
3.2.9 MPA1 test
3.2.10 MPA iteration
3.3. SSA chip
3.3.1 Requirements
3.3.2 Design SSA Front-End
3.3.3 Production SSA-Light prototype
3.3.4Test
3.3.5Documentation
3.3.2 Design iteration SSA1
3.3.3 Production SSA1
3.3.9 SSA1 test
3.3.10 SSA iteration
3.4. MaPSA
3.4.1 Design MaPSA-Light prototype
3.4.1.1. Establish requirements
3.4.1.2. Evaluate alternative designs/fabrication sources
3.4.1.3. Check compatibility with MPA and system
3.4.1.4. Evaluate testability
3.4.1.5. Design and review
3.4.2 Define procurement framework
3.4.3 Market survey (formal)
3.4.4 Production MaPSA-Light prototype
3.4.5 Iteration (second source etc)
3.4.6 Testing MaPSA-Light prototype
3.4.5.1. Define and prepare test bench and vectors
3.4.5.2. Test Functionality
3.4.5.3. Test Environmental resistance
3.4.7 Documentation
3.4.8 Full MaPSA mockup
3.4.8 Design iteration for full MaPSA prototype
3.4.9 Production of full prototype MaPSA1
3.4.10 Test of full prototype
3.4.11 MaPSA iteration
3.5. PS Front-End Hybrid
3.5.1 Design FEH-Light
3.5.2 Production FEH-Light
3.5.3 Test FEH-Light
3.5.4 Design FEH mockup
3.5.5 Production FEH mockup
3.5.6 FEH iteration
3.5.7 Test FEH prototype
4. Link
4.1. Low power GBT chip
4.1.1 Design
4.1.1.1. Establish requirements
4.1.1.2. Evaluate architectures and technologies
4.1.1.3. Evaluate packaging
4.1.1.4. Check compatibility with hybrid and system
4.1.1.5. Design and review
4.1.2 Production
4.1.3 Packaging
4.1.4 Testing (chip level)
4.1.2.1. Define and prepare test bench and vectors
4.1.2.2. Test functionality
4.1.5 Documentation
4.1.6 Design iteration
4.2. Low power GBLD chip
4.2.1 Establish requirements and options
4.2.2 Design
4.2.3 Production
4.2.4 Test
4.2.5 GBLD Iteration
4.3. GBTIA chip
4.3.1 Iterate Design (V2)
4.3.2 Iterate Design (V3)
4.3.3 Production
4.3.4 Test
4.3.4 GBTIA Iteration
4.4. VTRx+
4.4.1 Feasibility study (small footprint)
4.4.1.1. Study concept and options (mechanical and electrical interfaces)
4.4.1.2. Fabricate prototype based on VL components + connector clip
4.4.1.3. Evaluate performance and conclude on feasibility
4.4.2 Rolling market survey of small footprint packages
4.4.3 Prototype low power small footprint LP-SF-VTRx
4.4.4 Procurement Framework
4.4.5 VTRx+ Development
4.5. Optical Cabling
4.5.1 Check versatility of multi-ribbon cable
4.5.2 Cabling concepts
4.6. Backend opto
4.6.1 Survey MTx and MRx
5. Power
5.1. Powering architecture and system design
5.2. DC-DC 2.5 converter
5.3. DC-DC 1.2 converter
5.4. tripple DC-DC module
5.5 LVPS
5.6. HVPS
5.7. Electrical cables
5.8. Powering system
6. DTC
6.1. GLIB-based prototype backend
6.2. FC7-based prototype backend
6.3. DTC design
8xCBC2
hybrid
SF-VL Feasibility
Low Power GBT Feasibility
CBC2 chip
MPA-light chip
VTRx+ demonstrator
Tested MaPSA1
GBLD V4.1
Low Power GBLD V5
TDR
TP
Concentrator V2 in FPGA
CBC3
CBC4
CIC1
2xCBC2 chain
8xCBC2 chain
GBLD feasibility V4
GBTIA feasibility V1
2xCBC2 hybrid
2xCBC2
8xCBC2
Concentrator V3 in FPGA
CBC2 Hybrid Test System
GBTIA V2.1
GBTIA V2
M-Ribbon cable
versatility
8xCBC3 chain
8xCBC3
Tested CIC1
8xCBC2 2nd source
2xCBC3
GLIB-based FED/FEC
Tested CBC2
Tested MPA-light
Tested GBLD V4.1
Tested GBTIA V2.1
MaPSA-Light
MPA1
Concentrator data formats
Concentrator Spec
8xCBC2 environmental
and stress test
Diff lines choice
SSA Front-end
SSA1
Tested SSA1
Tested MPA1
SEH Demonstrator
FEH-Light
FEH Mockup
Tested FEH
SEH Prototype
Final Service Hybrid
CIC2
Final Front-End Hybrid
Final MPA
CBC4+CIC2
Final SSA
Final Full MaPSA
Final FEH
LP-GBT
Prototype
GBLD10
LDQ10
final LDQ10
VTRx+ Feasibility
Final VTRx+
Definition of powering scheme
Tk-grade UpFeast
DC/DC proto
DC/DC V1
Final DC/DC
FC7-based
FED/FEC
DTC general
specification
DTC V1
DTC V2
ready for test systems
TP'
EDR
Tested CBC3
Selected companies for Hybrid development
8xCBC3 + CIC1
CBC3+CIC1 Hybrid Test System
MaPSA MS
MaPSA1
IT
MaPSA-Flipped
Tested MaPSA-Flipped
FEH
Tested CBC4
Tested CIC2
GBLD V4.2
GBTIA2.5
VTRx+ Development Contract
Cabling Feasibility
Start Off detector prod
Start On detector Prod
MaPSA Mockup
module proto
test module V1
Modules ready
25% Modules
50% Modules
TIF system ready
100% Modules
Installation P5
Tracker Ready
DTC final
DTC generic
building blocks
Tested MaPSA-Light
LDQ10+
Note on M46: CBC submission (HL) 06/10/2016
Note on N47: CBC validated (LL) 15/06/2017
Note on R49: IC funding ends Q1-19
Note on S49: CBC submission (HL) 28/11/2019
Note on M63: CIC_mono submission (LL) 15/12/2016
Note on P65: CIC_dual submission (HL) 22/03/2018
Note on Q65: CIC_dual validated (LL) 29/11/2018
Note on S65: MPA/SSA/CIC submission (HL) 28/11/2019
Note on L78: Close Hybrid Market Survey (LL) 24/03/2016
Note on P88: 2S FEH order (LL) 08/03/2018
Note on Q88: 2S FEH validated (LL) 23/08/2018 Launch Hybrids Invitations to Tender (LL) 24/01/2019
Note on S88: Place hybrids contract (LL) 28/11/2019
Note on L96: 2S SEH demo order (LL) 21/04/2016
Note on M97: 2S SEH demo validated (LL) 29/12/2016
Note on O99: PS ROH proto order (LL) 05/01/2018
Note on P99: 2S SEH proto order PS POH proto order (LL) 17/05/2018
Note on Q100: PS ROH proto validated (LL) 14/09/2018 2S SEH proto validated (LL) 24/01/2019 PS POH proto validated (LL) 24/01/2019
Note on S101: Place hybrids contract (LL) 28/11/2019
Note on N111: MPA/SSA submission (HL) 23/03/2017
Note on O113: MPA/SSA validated (LL) 11/01/2018
Note on S114: MPA/SSA/CIC submission (HL) 28/11/2019
Note on N121: MPA/SSA submission (HL) 23/03/2017
Note on O123: MPA/SSA validated (LL) 11/01/2018
Note on S124: MPA/SSA/CIC submission (HL) 28/11/2019
Note on Q145: Launch MaPSA Call for Tender (LL) 27/12/2018
Note on L151: PS FEH demo order (LL) 16/06/2016
Note on N151: PS FEH demo validated (LL) 23/02/2017
Note on O152: PS FEH proto order (LL) 14/12/2017
Note on Q153: PS FEH proto validated (LL) 23/08/2018
Note on S153: Place hybrids contract (LL) 28/11/2019
Note on S163: Francois Vasey: l Specification Q2 2015 l Full chip prototype out for manufacture Q4 2016 l Full chip prototype testing Q3 – Q4 2017 l Final Engineering run sent out Q2 2018 s First chips available to users Q4 2018 l First production batch available for users Q4 2019 l Completion of production Q4 2020
Note on R168: First lpGBT production batch available (LL) 19/07/2019
Note on M199: Power system specs defined (FD) (LL) 15/12/2016
Note on P201: DC-DC proto validated (LL) 08/03/2018
Note on O206: 1st proto power distribution system built (LL) 13/12/2017
Note on Q206: OT Power distribution proto system built (HL) 14/11/2018
Note on AC206: Powering system ready for TK (HL) 04/12/2024
Note on M211: DTC System specs defined (FD) (LL) 15/12/2016
Note on O211: 1st proto DTC system built (LL) 13/12/2017
Note on Q211: Proto DTC system built (HL) 12/12/2018
Note on AC211: DTC system ready for TK (HL) 04/12/2024